PERSONAL OPERATING PLAN  /  MANAGER REVIEW EDITION

# Shailesh Pilare
ATMOS Operating & Learning Plan

Hardware foundations → credible evidence → OEM and partner decisions

One-, three-, and six-month checkpoints | Annual continuation to August 2027

Owner: Shailesh Pilare · Sponsor for review: Raj
Role: Senior Principal AI Solutions Architect, as stated in the original plan
Proposed revision 2.0 · Prepared 23 September 2026 · Internal working document

The next six months are about learning the hardware well enough to explain it, testing the assumptions that matter, and guiding an adoption decision. Videos and slides support those outcomes; they are not the outcomes themselves.

| Horizon | What we are trying to achieve | Evidence of completion |
| --- | --- | --- |
| 1 month | Understand the server and the three ATMOS layouts; agree scope and establish a reproducible workflow. | Engineer-reviewed hardware map, owned questions, versioned profiles, one causal microtrace, and a lab-access plan. |
| 3 months | Demonstrate a bounded bridge model, establish available conventional controls, and select the lead product experiment. | Reproducible memory-path study, limited LLM/MoE and vector examples, calibration or explicit gaps, OEM checklist, and a decision memo. |
| 6 months | Turn surviving evidence into an engineering handoff and a jointly scoped OEM/partner evaluation. | Reviewed comparison and economics envelope, reproducible backend package, two reference packages, and a continue/hold/stop decision. |

The original annual ambition remains: reusable software, five approved reference packages, customer evaluations and POCs, field adoption, and executive decisions. These goals depend on engineering support, approved data, partner access, and hardware readiness. This plan does not assert that any outcome is already completed. [S1 §§1–2]

Planning boundary: No product specification, hiring allocation, partner delivery, spend approval, or customer commitment is created by this document. Dates and new thresholds are proposals to agree with Raj.

PLAN  •  EVIDENCE  •  DECISIONS

# Start here: how to use the plan

The original 17-section backbone is retained. The learning curriculum now starts with ordinary hardware, while the delivery plan explicitly separates understanding, simulation, measurement, integration, and adoption. Appendix C explains what changed. [S1; S2; S3]

| 1. North star and priorities | 3 |
| --- | --- |
| 2. Success contract and annual goals | 4 |
| 3. Time, staffing, and resources | 5 |
| 4. Daily and weekly operating rhythm | 6 |
| 5. Stakeholders and ownership | 7 |
| 6. Meeting playbooks | 9 |
| 7. Artifacts and source control | 11 |
| 8. Learning curriculum and video sequence | 12 |
| 9. Code, hardware, and POC roadmap | 19 |
| 10. Month-by-month execution plan | 24 |
| 11. Customer, partner, and economics workflow | 32 |
| 12. Metrics dashboard | 33 |
| 13. Development and visibility | 34 |
| 14. Risks and contingencies | 35 |
| 15. Monthly review template | 36 |
| 16. Weekly planning template | 37 |
| 17. Definition of a good year | 38 |

Appendices A–D: glossary, worksheets, original-plan crosswalk, and sources.

## Calendar and status

T0 is the start date Raj agrees. For a concrete example, this edition uses 28 September 2026. Month 1 ends 27 October 2026; Month 3 ends 27 December 2026; Month 6 ends 27 March 2027. These are calendar months, not exact 30/90/180-day periods. Weekly packages are approximate; holidays, partial weeks, and access require adjustment.

The original September 2026–August 2027 annual period remains. April–August 2027 is the continuation after the reset; this does not silently extend the deadline into September 2027. Earlier work is status unknown until the first-week audit. [S1 §10]

Reading routes: Raj discussion: §§1–3 and 6. Daily learning: §8, in sequence. Build and test: §§9–10. Weekly control: §§4, 7, 12, 15–16. Reference material: appendices. Do not read the whole document before starting Lesson 1.

PLAN  •  EVIDENCE  •  DECISIONS

# 1. North star: make sound decisions happen

Retain the original mission: connect customer workload, architecture, engineering evidence, and adoption. Your responsibility is not to design every circuit. It is to identify the right requirements, get qualified owners to validate them, and make the trade-offs understandable. [S1 §1]

| Decision | What we must resolve |
| --- | --- |
| Product/workload | Is the lead E3.S case persistent-model inference, candidate-vector refinement, or another approved service? The current proposals differ. |
| Physical layout | Full-length eight-module card; direct-attached E3.S devices; or E3.S devices behind a separate PCIe-switch card? |
| Evidence and scope | What can be shown now, what requires a measured component, and what requires complete ATMOS execution? |

## Recommended order for this reset

First: understand the hardware and establish one common memory-path study. Learn the topology while building only what is needed to explain capacity, queues, dependencies, and data movement.

Second: retain a small LLM/MoE control and one E3.S retrieval example. Recommend candidate refinement as the first deeper E3.S product experiment after the common path. The reviewed Bridge addendum makes HBF-active retrieval central, while earlier documents lead with neural services. Raj must approve the selected scope; do not silently combine every proposed minimum release. [S2 §11.5; S4; S5; S6]

Third: qualify the deployment path. Begin OEM and partner questions early, but do not promise a working device or performance before corresponding evidence exists.

## Three questions every engagement must answer

Does the proposed configuration solve an important problem? Is there objective evidence it can work? Can the operator adopt and support it at acceptable cost and risk? [S1 §1]

Not now: a new chip-verification program, full compiler, production driver, universal CUDA replacement, every vertical POC, or another unsupported winner map. A new initiative must displace an existing priority.

PLAN  •  EVIDENCE  •  DECISIONS

# 2. Success contract: capability plus evidence

Use explain → apply → validate → hand off as the progress standard. Completion means someone can review or reproduce an artifact, not that a video or meeting was attended. The checkpoint criteria below are recommendations to agree. [S1 §§2, 8, 12]

| Checkpoint | Personal capability | Delivery gate |
| --- | --- | --- |
| Month 1 | Identify parts; trace local/host/peer paths; distinguish capacity, rate, latency, and evidence classes. | Hardware owner reviews the three-layout map; critical unknowns have owners; one small causal test is reproducible. |
| Month 3 | Explain an observed control and a modeled bottleneck; distinguish compute, NUMA, PCIe, and memory effects. | Bounded comparison, negative control, source-linked profiles, and an internally accepted next-stage charter. |
| Month 6 | Lead an architecture/OEM workshop; explain calibration limits and cost sensitivity; hand off a test package. | Another engineer reproduces the package; product/architecture disposition major gaps; partner evaluation or blocker is documented. |

## Annual outcomes retained from the original

| By August 2027 | What counts |
| --- | --- |
| Architecture authority | Five approved, evidence-linked reference packages used by field or product. |
| Technical/software contribution | Repeatable Virtual ATMOS capability, maintained placement policy, and at least one runtime path or accepted handoff. |
| Customer traction | Three qualified evaluations, two executed POCs, and one design-partner/platform-shortlist decision, subject to external dependencies. |
| Product and field impact | Prioritized requirements with dispositions; discovery, sizing, POC, and enablement tools adopted by others. |
| Executive and personal impact | Monthly memos and quarterly decisions; cross-functional feedback and evidence of increasing responsibility. |

Operating rules: preserve confidentiality; never relabel projections as measurements; agree POC gates before results; close meetings with owner/date; preview material with Raj; protect deep work; stop work with no useful decision or reusable output. [S1 §2]

PLAN  •  EVIDENCE  •  DECISIONS

# 3. Time budget, support, and trade-offs

The original allocation was 20/30/20/15/10/5 percent across the six portfolios below. Increase foundational learning temporarily rather than trying to add it on top of a full build schedule. [S1 §3]

| Portfolio | Month 1 | Months 2–3 | Months 4–6 |
| --- | --- | --- | --- |
| Learning and applied architecture | 35% / 14 h | 20% / 8 h | 15% / 6 h |
| Code, modeling, tests, measurements | 25% / 10 h | 35% / 14 h | 35% / 14 h |
| Customer, field, partner preparation | 10% / 4 h | 15% / 6 h | 20% / 8 h |
| Product and engineering decisions | 15% / 6 h | 15% / 6 h | 15% / 6 h |
| Reports, runbooks, enablement | 10% / 4 h | 10% / 4 h | 10% / 4 h |
| Mentoring, feedback, impact record | 5% / 2 h | 5% / 2 h | 5% / 2 h |

This is one 40-hour planning week, not extra evening work. Commit about 32 hours to named deliverables and leave 8 hours within these allocations for interruptions and review. Keep at most three major outcomes active: evidence/build, architecture/product, and partner/customer.

## Staffing dependency

The Bridge proposal assumes you as accountable owner plus 0.5–1.0 modeling engineer, 0.1–0.2 architecture, 0.1 compiler/NPU, 0.1 memory/firmware, 0.1–0.2 DevOps/test, and a named partner liaison. These are source estimates, not people already assigned. [S2 §10.2]

Supported route: pursue a staged Month 3 candidate and Month 4 hardening. Solo/reviewer-only route: keep profiles, golden resource tests, one workload adapter, and a requirements report; defer a second deep adapter, advanced UI, and production integration. Rebaseline in Week 2.

## Resources to request

Approved Linux development environment and repository; read-only lab/OEM access; scheduled GPU-control time; synthetic or authorized traces; architecture profile owner; hardware mentor; modeling reviewer; partner tool/license access if available. Get current quotes and a sponsor-approved spend ceiling before procurement. An accessible conventional host is more useful now than an unqualified large purchase.

PLAN  •  EVIDENCE  •  DECISIONS

# 4. Daily and weekly operating rhythm

Keep the original discipline, but let Month 1 deep work include guided study and applied diagrams. The sequence is more important than rigid clock times. [S1 §4]

| Daily block | Activity | Concrete output |
| --- | --- | --- |
| Start: 20 min | Review plan, permissions, actions, and blockers | “Today succeeds if…” |
| Protected: 2 h | Learn/apply or build/test | Saved drawing, code, calculation, or experiment |
| Record: 20 min | Capture versions and evidence | Reproducible state and concise change note |
| Collaboration: 60–90 min | Ask one bounded engineering question | Correction, decision, or assigned action |
| Second work block | Apply findings or prepare a review | Updated artifact, not another reading list |
| Meeting window | Batch required stakeholder work | Owner, due date, and outcome |
| Close: 20 min | Save work, follow up, plan restart | Tomorrow’s first task |

Daily blocks fit within the weekly allocation. Protect at least four two-hour blocks each week. Do not schedule learning and implementation as if they use different people’s time.

## Weekly rhythm

Monday: select three outcomes and the changed experiment variable. Tuesday: learn/build. Wednesday: measure or review correctness. Thursday: engage engineering/field. Friday: reproduce, demonstrate, and synthesize.

## Start and close checks

At the start, identify the decision consuming your work, the applicable source revision, the data classification, and one must-finish task. At the end, save the configuration/result, update action and assumption registers, send follow-ups, record one learned fact and one open question, and define the next action.

## Friday evidence note—one page

What was proved, disproved, or decided? What can another person reproduce? Which product/customer decision moved? Which assumption or claim changed? What should stop next week? Link detailed logs rather than copying them into the note.

Recovery rule: a missed day or confusing lesson is not a personal failure. Resume at the next incomplete artifact, ask a specific question, and remove lower-priority work. Do not create a compensating weekend program by default.

PLAN  •  EVIDENCE  •  DECISIONS

# 5. Stakeholders: sponsors and working partners

Names and roles below are retained from the original plan as working assumptions. Confirm current responsibilities and availability with Raj; this is not a verified organizational directory. [S1 §5]

| Stakeholder | Proposed cadence | What you bring | Outcome sought |
| --- | --- | --- | --- |
| Raj | Weekly 30-minute 1:1; monthly decision review | One-page evidence note, priorities, trade-offs | Scope, sponsorship, support, escalation |
| Gopal | Weekly for an active account | Workload analysis and approved narrative | Qualified discussions and coherent account action |
| Eric | Biweekly; at architecture gates | Paths, input assumptions, sensitivities | Architecture truth, owners, access route |
| Anil | Monthly or at economics gates | Cost boundary, quote gaps, adoption inputs | Reviewed price/performance requirements |
| Praveen | Biweekly | Discovery questions and no-fit examples | Real workload signal and field feedback |

## First-month relationship objective

Secure one hardware mentor and one modeling reviewer. Do not independently schedule every specialist every week. Ask the hardware mentor for three short sessions: ordinary server anatomy; the three ATMOS layouts; and correction of your final path drawing.

Bring your attempted explanation first. The fastest review is “Here is my map; which connection is wrong?” rather than “Please explain hardware.”

## Forums with a purpose

Use the relevant program-risk, architecture/specification, bring-up/validation, and runtime forums. Add a customer-account sync only when work is active. Add partner/API review when a liaison exists. A monthly evidence forum should consolidate reviews, not multiply meetings. [S1 §5; S2 §12]

Meeting rule: you need not answer every electrical or firmware question yourself. State the evidence, identify the correct owner, and record when the answer is needed. Do not turn a draft interpretation into an engineering commitment.

PLAN  •  EVIDENCE  •  DECISIONS

# 5. Stakeholders: engineering ownership

Use this routing sheet to obtain the required artifact. Initial contacts come from the original plan and must be confirmed. [S1 §5]

| Area / original contact | First question | Requested evidence |
| --- | --- | --- |
| ASIC — Carl | What is committed, measured, deferred, or at risk? | Controlled block/capability revision |
| Backend — Piyush | Which destinations and controller limits apply? | HBF/LPDDR/NoC path and service profile |
| Firmware/software — Vishwas | Which queues, DMA, reset, and APIs can be tested? | Interface, error, and telemetry contract |
| Hardware — Steve | Which packaging, lanes, power, and cooling are valid? | Board/bay/slot lane map and design guide |
| Systems — John | What defines a working full platform? | Bring-up and integration acceptance list |
| Program operations — PK Sharma | How are dependencies and changes governed? | Change and decision process |
| PTDI — Ashok | Which diagnostics or test evidence are reusable? | Approved counters and fixtures |
| Test working group — Sathya | Which workload failures are covered? | Coverage and validation-owner map |
| Schedule — Gurjit | Which dates and access dependencies are authoritative? | Controlled milestone record |
| Bring-up — Eshak | What works now and what can be measured? | Available configurations and known issues |
| Partner liaison — assign | What exists now versus a later deliverable? | Statement of work, API, licensing, tests |

## Your ownership boundary

Own: workload definitions, scenario/profile quality, system-level reasoning, evidence lineage, follow-through, and decision reports.

Co-own: test design, baseline validity, simulator contracts, runtime requirements, and OEM acceptance criteria.

Do not self-certify: signal integrity, electrical compatibility, thermal limits, secure isolation, final silicon timing, license rights, or launch readiness. Obtain the qualified owner’s review.

Every unresolved question needs an impact, owner, requested artifact, review date, and interim assumption. Escalate a blocked input rather than silently replacing it with a favorable number.

PLAN  •  EVIDENCE  •  DECISIONS

# 6. Meeting playbooks: the next Raj discussion

Purpose: agree a focused reset. Send a one-page pre-read the prior business day when possible. The detailed plan supports the discussion; it is not the agenda to read aloud. [S1 §6]

| Time | Walkthrough | Decision |
| --- | --- | --- |
| 0–5 min | One-, three-, six-month outcomes | Agree what success means |
| 5–12 min | Three physical layouts and unknown paths | Select baseline and hardware owner |
| 12–18 min | One memory/queue example and evidence boundary | Select the first causal test |
| 18–25 min | Learning, modeling support, lab and partner access | Assign mentor, reviewer, access, liaison |
| 25–30 min | Priorities and deferrals | Agree next artifact, owner, review date |

## Bring three things

One-page outcomes; a full-card/direct-E3.S/switched-E3.S comparison; a five-question register. Do not bring seven competing proposals without explaining which is authoritative.

## Opening you can rehearse

“I am connecting the workload work to the physical deployment. First I will validate the three ATMOS layouts and the memory path with the hardware owner. In parallel, I will build a small reproducible resource test. By one month we should have reviewed profiles and a causal example; by three months a bounded comparison and the lead POC; by six months a calibrated package and partner/OEM path, subject to access.”

## Recurring manager 1:1

Retain the original structure: outcomes 5 minutes; changed evidence 5; priorities/trade-offs 8; decisions/escalations 8; commitments/visibility 4. Close with: What should stop? Which assumption needs escalation? Who reviews the next artifact? Record the answers that day.

## Readiness check

Explain E3.S versus PCIe; locate compute and switch; distinguish local, host, and peer traffic; identify what is measured versus assumed. Unresolved quantities are acceptable when visible and owned. Invented certainty is not.

PLAN  •  EVIDENCE  •  DECISIONS

# 6. Other reviews and follow-up

These retain the original forum types and intended outcomes. [S1 §6]

| Forum | Agenda | Required output |
| --- | --- | --- |
| Engineering architecture — 60 min | Decision; paths; workload; alternatives; failures/security; validation | Architecture decision and validation owner |
| Product — 45 min monthly | Customer problem; evidence; fit; gap; alternatives/economics | Commit, investigate, defer, or reject a requirement |
| Executive — 30 min quarterly | Objective; three insights; pipeline; risks; next gates; at most two asks | Recorded resource/priority/stop decision |
| Customer discovery — 60 min | Outcome 10; workload 15; platform 15; operations 10; hypothesis 5; next step 5 | Quantified problem and authorized data request |
| POC kickoff — 60 min | Decision; baseline; trace; quality/latency; gates; data/IP; responsibilities | Joint charter before comparative runs |
| POC closeout — 60 min | Hypothesis; reproducibility; results/limits; failures; TCO; decision | Written proceed, iterate, pause, or stop |

## Questions for every technical workshop

Hardware: Where is compute? Where is each memory? Which connection is shared? What generation/width is negotiated? Which peer paths are supported?

Workload: What arrives and when? What is resident, what is actually accessed, and which bytes cross each boundary? What latency and quality must hold?

Evidence: Did the backend execute numbers, simulate timing, or observe a partner block? Which input dominates uncertainty? What result would disconfirm the hypothesis?

## Follow-up format

Send decision, rationale, evidence link, owner, date, and open issue. Attach detailed logs only when useful. Preview material with Raj and the relevant owner before asking them to defend it in a wider forum.

A POC kickoff is not permission to make a product promise. External performance, compatibility, pricing, or availability wording must be approved by the authorized product, engineering, and communications/legal owners.

PLAN  •  EVIDENCE  •  DECISIONS

# 7. Artifact and source-control system

Maintain one controlled workspace and index. Reuse these artifacts rather than creating a new document family for each discussion. [S1 §7]

| Artifact | Cadence | Done means… |
| --- | --- | --- |
| Plan and weekly board | Weekly | Three outcomes, dates, owners, blockers |
| Hardware/system map | Weekly initially; on change | Three layouts, named paths, owner corrections |
| Workload card and run manifest | Per experiment | Versions, traffic, policies, configuration, gates |
| Evidence note / decision memo | Weekly / monthly | Result, reproducibility, limits, next decision |
| Architecture decision record | At a material choice | Options, trade-offs, owner, validation |
| POC report / reference architecture | At gates | Quality, failures, cost, operation, and adoption boundary |
| Field kit / competitive brief | Quarterly | Reusable, current, sourced, and approved |
| Impact log | Weekly | A decision moved or another person used the work |

## Six registers, one index

Decisions: why/owner/date. Assumptions: source/range/confidence/expiry. Risks: trigger/impact/response. Claims: wording/evidence/approval/audience. Customer actions: stage/owner/date. Product evidence backlog: need/value/acceptance/disposition.

## Resolve the document conflicts

An approved controlled engineering release outranks a proposal. Recommend using the reviewed Bridge draft [S2] as the implementation-planning baseline, subject to Raj’s agreement. The previously discussed Rust/C++ design [S8] remains an alternative and source of reusable contracts; do not assume both need implementation.

The inference proposal [S4] and retrieval proposals [S5–S6] have different lead workloads. The reviewed Bridge addendum also differs from its earlier roadmap. Record the selected minimum release and explicitly deferred adapters.

## Confidentiality

Keep customer traces, restricted architecture, partner collateral, credentials, and unreleased claims internal. Generalizable FlashKV code may be shared only after approval and sanitization. If legacy material creates a concern, notify the authorized owner; this plan does not assert an incident. [S1 §§2, 9]

LEARN  •  EXPLAIN  •  APPLY  •  REVIEW

# 8. Learning curriculum: from level zero

The curriculum now starts before the original GAIA-specific reading list. Use watch → identify → explain → apply → review. Record only three notes per lesson: what it does; where it is in our drawing; what engineering must confirm. [S1 §8; new learning sequence]

| Group | Learn in this order | Apply it to | Horizon |
| --- | --- | --- | --- |
| A. Ordinary server | Board, CPU, cores, RAM, DIMMs, storage, cooling | Label a server and trace a file-processing task | First days |
| B. Connections and packaging | PCIe, slots/lanes, switches, MCIO, backplane, E3.S, NUMA | Three physical ATMOS layouts | Weeks 1–2 |
| C. Accelerator/SoC | GPU/NPU, HBF, LPDDR, SRAM, HIM, NoC, DMA, queues | Local data path and its possible bottleneck | Weeks 2–6 |
| D. Server to rack | NIC/network, RDMA, firmware, power, failures, Kubernetes | Two-node topology and service boundaries | Months 2–3 |
| E. Serving | Prefill/decode, KV, MoE, TP/EP, replicas, vector scoring | Fair profiles and result interpretation | Months 1–3; then deepen |

## First two study days

Day A: lessons 1–3, 5, 7; about 2–3 hours with pauses. Produce a labeled server and an explanation of CPU, RAM, and storage.

Day B: lessons 8–12; about 2–3 hours with pauses. Skim E3 sections of lesson 10 now and revisit later. Draw the three configurations and write five questions. Finish remaining lessons during Month 1.

These are recommended study budgets, not stated video runtimes. Desktop and older platform examples teach concepts, not current OEM specifications. Service demonstrations are observation exercises, not authorization to modify hardware.

Link status: the prior video sequence is preserved. Publisher/indexed pages were checked where accessible on 23 September 2026; several direct YouTube fetches failed. Full playback, captions, regional availability, and exact durations were not verified. Use the publisher fallback where supplied; recheck access before a group session.

LEARN  •  EXPLAIN  •  APPLY  •  REVIEW

# 8. Video sequence: ordinary computer parts

These exercises are the plan’s assignments; the linked material supplies the lesson. Study allowances include pauses and notes, not only playback.

### 1. Explaining Desktop PC Hardware — ExplainingComputers

YouTube · Publisher / creator reference

Focus: Motherboard, processor, memory, storage, expansion card, and power supply. Apply: Label six physical objects in a paused image. Self-check: Which component executes instructions, and which keeps a saved file? Study allowance: 25–35 min. [V1]

### 2. How Do CPUs Work? — ExplainingComputers

YouTube · Publisher / creator reference

Focus: Instruction execution and the processor’s relationship with memory. Apply: Describe reading two values, adding them, and keeping the result. Self-check: Distinguish the server, CPU package, core, and socket. Study allowance: 25–35 min. [V2]

### 3. Explaining RAM — ExplainingComputers

YouTube · Publisher / creator reference

Focus: Working memory versus persistent storage; physical memory modules. Apply: Calculate eight 32 GB modules as 256 GB capacity, not bandwidth. Self-check: Explain RAM, DRAM, DIMM, and memory slot at different levels. Study allowance: 25–35 min. [V3]

### 4. Memory Technologies — Professor Messer

YouTube · Publisher / creator reference

Focus: Memory channels and error-correction vocabulary. Apply: Ask which DIMM population rules apply to the selected server. Self-check: Does equal capacity guarantee equal memory performance? Study allowance: 20–30 min. [V4]

LEARN  •  EXPLAIN  •  APPLY  •  REVIEW

# 8. Video sequence: server and PCIe connections

These exercises are the plan’s assignments; the linked material supplies the lesson. Study allowances include pauses and notes, not only playback.

### 5. RAM replacement: PowerEdge R520 — Dell

Dell-hosted video

Focus: Actual DIMMs, clips, slots, heat sinks, and the surrounding server board. Apply: Recognize the same objects in an OEM system diagram. Self-check: Point to memory without confusing it with the processor cooling assembly. Study allowance: 15–20 min. [V5]

### 6. Explaining Motherboard Chipsets — ExplainingComputers

YouTube · Publisher / creator reference

Focus: Connection diagrams among CPU, memory, and other devices. Apply: Draw a basic host map and mark server-specific paths that remain unknown. Self-check: Why is a motherboard not another application processor? Study allowance: 25–35 min. [V6]

### 7. Explaining PCIe Slots — ExplainingComputers

YouTube · Publisher / creator reference

Focus: Slot, generation, and lane-width terminology. Apply: Read a Gen5 x4 label and list what still needs measurement. Self-check: Separate physical slot size from electrically available lanes. Study allowance: 30–40 min. [V7]

### 8. Interop Lab Bulletin #3: PCIe Switches — Astera Labs

YouTube

Focus: Host and device ports; switch routing versus signal restoration. Apply: Locate the switch in a full card and a separate-switch-card arrangement. Self-check: Which connection is shared, and which traffic actually uses it? Study allowance: 20–30 min. [V8]

Checkpoint: connector, cable, slot, link, and switch are different things. A supported peer path must still be verified.

LEARN  •  EXPLAIN  •  APPLY  •  REVIEW

# 8. Video sequence: E3.S, backplanes, and MCIO

These exercises are the plan’s assignments; the linked material supplies the lesson. Study allowances include pauses and notes, not only playback.

### 9. Explaining SSDs: Form Factors, Interfaces & Technologies — ExplainingComputers

YouTube

Focus: Physical package, communication interface, and storage protocol. Apply: Make three columns: shape, connection, function. Self-check: Why are E3.S, PCIe, NVMe, and NPU not alternatives? Study allowance: 25–35 min. [V9]

### 10. The Latest in Form Factors — SNIA-linked presentation

YouTube · Publisher / creator reference

Focus: EDSFF and E3 packaging; device versus bay versus backplane. Apply: Annotate the E3.S device location on the ATMOS photograph. Self-check: Does a thicker device automatically receive more lanes? Study allowance: 30–45 min selected content. [V10]

### 11. EDSFF backplane replacement: PowerEdge R570 — Dell

Dell-hosted video

Focus: Board behind the devices, and its power/data connections. Apply: Label the backplane and cables in your own diagram. Self-check: How is a passive backplane different from an active switch card? Study allowance: 15–20 min. [V11]

### 12. Mini Cool Edge IO Cable Assembly — Amphenol Tech Demo

YouTube · Publisher / creator reference

Focus: Recognize the MCIO connector, cable assembly, and board attachment. Apply: Trace bay/backplane → cable → switch card → host. Self-check: Why does the cable label not fully specify logical port routing? Study allowance: 15–25 min. [V12]

Checkpoint: redraw all three ATMOS layouts. Viewing a service procedure is not authorization to change a live server.

LEARN  •  EXPLAIN  •  APPLY  •  REVIEW

# 8. Video sequence: locality and operation

These exercises are the plan’s assignments; the linked material supplies the lesson. Study allowances include pauses and notes, not only playback.

### 13. NUMA Deep Dive — Johan van Amersfoort and Frank Denneman

YouTube

Focus: CPU sockets and local versus remote host memory. Apply: Draw two CPU/memory domains and place a device connection. Self-check: Distinguish host-memory locality from PCIe peer routing. Study allowance: 40–60 min in two passes. [V13]

### 14. How Do Graphics Cards Work? Exploring GPU Architecture — Branch Education

YouTube

Focus: Complete card, processor, device memory, and on-chip working storage. Apply: Compare host RAM with GPU memory, then the roles in NPU/HBF/LPDDR. Self-check: Where do resident weights live, and where are current tiles used? Study allowance: 40–60 min. [V14]

### 15. The BIOS — Professor Messer

YouTube · Publisher / creator reference

Focus: Startup, initialization, and handoff to the operating system. Apply: Ask which BIOS, BMC, driver, and runtime versions the lab needs. Self-check: Why is physically inserting a device not enough to run a service? Study allowance: 20–30 min. [V15]

### 16. Cooling — Professor Messer

YouTube · Publisher / creator reference

Focus: Airflow, heat sinks, fans, and component layout. Apply: Write thermal questions for fully populated E3.S bays. Self-check: Separate a power specification, measured draw, and cooling qualification. Study allowance: 20–30 min. [V16]

Checkpoint: explain how data delivery can limit available compute. Older platforms and GPU examples do not establish current ATMOS specifications.

LEARN  •  EXPLAIN  •  APPLY  •  REVIEW

# 8. Next layer: networking and serving

Complete physical recognition first. These resources extend the networking and LLM tracks; the exercises are proposed assignments, not product claims.

### 17. Networking Devices — Professor Messer

Video and transcript

When: Month 2. Apply: draw host → NIC → network switch → second host. Check: distinguish an Ethernet switch between servers from a PCIe switch within a server. Study: 30–45 minutes. [R5]

### 18. Mixture of Experts — NVIDIA

Introduction and embedded video

When: late Month 1 or early Month 2. Apply: show a token moving to a resident expert, then a separate weight-loading event. Check: total parameters, activated parameters, and fetched bytes are different. Study: 25–35 minutes. Vendor comparisons are not ATMOS evidence. [R6]

### 19. NCCL: The Inter-GPU Communication Library Powering Multi-GPU AI

NVIDIA GTC session

When: Month 3 after basic parallelism. Apply: identify reduction, gathering, expert dispatch, and point-to-point needs. Check: a communication API does not guarantee an ATMOS transport. Study: 45–60 minutes; player access may require sign-in/JavaScript. [R7]

## Read alongside the videos

LLM benchmarking fundamentals for TTFT, TPOT, request rate, and concurrency; vLLM parallelism and expert deployment for group semantics; Kubernetes architecture for service versus device responsibilities. [R8–R10]

Deliverable: one LLM flow and one vector-service flow identifying CPU, device memory, compute, network, queues, and output. For RDMA and the selected NIC, obtain a walkthrough using the real topology. Advanced NoC, CXL, and compiler courses follow only when an experiment requires them.

LEARN  •  EXPLAIN  •  APPLY  •  REVIEW

# 8. Internal curriculum and proficiency checks

Public lessons establish vocabulary; controlled architecture material establishes the actual device. Do not infer module acronym expansions or memory destinations without the owner’s confirmation. [S1 §8; S2 §§5, 7; S4 §5]

| Area | Learn enough to explain | Applied proof / reviewer |
| --- | --- | --- |
| HIM / host interface | Commands, mappings, DMA, interrupts, completion, reset | Command-to-completion trace; firmware |
| HSC/HFCM and HBF | Access size, channels, outstanding limits, reads/writes, retry | Per-size and queue-depth profile; backend |
| NoC / AXI boundary | Routes, arbitration, shared links, backpressure | Competing-transfer microtrace; architecture |
| SRAM / CSC / buffers | Ownership, readiness, ring wrap, safe reuse | Full/empty/starvation/order tests; firmware |
| NPU/compiler | Operators, precision, tiles, launch, fallback | Capability and timing table; compiler |
| LPDDR | Capacity, channels, staging and KV traffic | Simultaneous fill/consume study; memory |
| Boot/security/RAS | Initialization, signed artifacts, isolation, recovery | Readiness/failure checklist; qualified owners |

## Rate skill through demonstration

0: unfamiliar. 1: recognize and name. 2: explain without notes. 3: define a test and interpret a result. 4: challenge assumptions and enable another engineer to reproduce the method.

By Month 1, target level 2 for ordinary server parts and the three layouts; level 1–2 for ATMOS internals. By Month 3, target level 3 for a selected memory path, workload, and topology. By Month 6, target level 4 for the evaluation method—not every silicon specialty. These are proposed goals, not a current assessment.

## Ten-question check

Explain a DIMM; root port; switch versus retimer; bay versus backplane; E3.S versus NVMe; host versus device memory; local versus peer traffic; capacity versus bandwidth; request rate versus concurrency; timing simulation versus numerical inference.

Defer RTL coding, electrical eye-diagram analysis, full coherence protocols, and custom kernels until a decision needs them and an appropriate mentor is available. Update the original personal system map as a living reference; do not force it to 20 pages merely to hit a document-size target. [S1 §8]

PLAN  •  EVIDENCE  •  DECISIONS

# 9. Code roadmap: build an evidence capability

Retain the original three streams—harness, placement policy, runtime integration—but use one approved architecture and repository strategy. The reviewed Bridge draft proposes Python/SimPy initially, with optional TokenSim and partner backends; the previously discussed Rust/C++ design is a separate implementation alternative. [S1 §9; S2 §6; S8]

| Stream | Initial build | Later, after evidence |
| --- | --- | --- |
| A. Bridge / Virtual ATMOS | Typed profiles, units, capacity, deterministic resources, queues, dependencies, and result bundles | Calibrated backends, selected multi-device/rack studies, reusable reports |
| B. Placement policy | Explicit admission, resident/tiered object placement, reason codes, supported fallback | Trace-driven prefetch/cache policy, topology-aware TP/EP, restore-versus-recompute |
| C. Runtime integration | Backend-neutral command/result contract and one adapter spike | A maintained framework/device path with tests and an accountable engineering handoff |

## The essential data flow

Scenario + model/data + topology + policy → serving/query adapter → normalized work and dependencies → finite hardware resources → completion events → metrics, traces, and calibration ledger.

The scheduler asks for work; the hardware model determines completion. Decide whether a run is fixed-trace replay or completion-fed scheduling. Do not let two layers independently assign the same token time. Search query records must not be forced into a fake token/KV model.

## Evidence ladder

Capacity arithmetic; analytical service model; discrete-event simulation; component-calibrated model; partner/RTL/FPGA observations; physical ATMOS. Each level supports a different claim. Numerical correctness requires an executing reference or actual implementation; timing simulation alone does not generate valid answers. [S2 §§3, 8, 11]

## Minimum useful release for this reset

One reviewed memory path; a bounded LLM/MoE demonstration; a vector-refinement demonstration; all three topology profiles; at least one measured conventional control when available; one common evidence format; and another engineer able to reproduce a reference run. This is a proposed scope substitution—not the full five-adapter MVR already delivered.

PLAN  •  EVIDENCE  •  DECISIONS

# 9. Hardware and OEM test track

Model and label these configurations separately. None is assumed qualified by the drawing. [S3 §§2–5; S4 §2; S7]

| Profile | Compute location / connection | First useful comparison |
| --- | --- | --- |
| A: full-length card | Eight local modules and switch on an internal AIC | Module-local versus card-local communication |
| B: direct E3.S pool | Individual bay devices through backplane/cables to host ports | Independent jobs and host-path limits |
| C: switched E3.S pool | Bay devices through MCIO to a separate switch AIC | Peer paths and shared-uplink contention |

Capture exact CPU/socket/DIMM population, bay/slot wiring, switch and retimer, negotiated generation/width, host affinity, BIOS/BMC, drivers, power/cooling limits, and device exposure. A server-family name is not a topology. Dell R770 is a useful anatomy reference, not a declaration of ATMOS compatibility. [S3; R1]

## First measurement sequence

Inventory and path discovery; workload-relevant local-memory test; host/device transfer; supported peer transfer; concurrent transfers; then actual workload. Keep default and explicitly aligned placement as separate controls.

| NUMA experiment | What remains fixed | Report |
| --- | --- | --- |
| Remote CPU only | Buffers and device | Submission/completion overhead |
| Remote host buffers only | CPU workers and device | DMA/host-memory path bandwidth and latency |
| CPU and buffers remote | Logical workload | End-to-end effect versus aligned control |
| Same NUMA, different PCIe branches | Model and rank count | Peer eligibility and path behavior |
| Cross-socket / interleaving | Only approved settings changed | Capacity, bandwidth, latency, interference |

No generic “remote NUMA penalty.” Record the actual source/destination, payload size, queue depth, copy count, and result. Unsupported routes are findings, not missing data to conceal.

Replacement rule: host DIMMs, cards, SSDs, and NICs change only within qualified combinations. On-card LPDDR/HBF and NoC/HIM logic are board/silicon/profile changes, not universal field swaps. Begin with read-only inspection; physical changes and fault tests need lab-owner approval. [S3 §§4–5]

PLAN  •  EVIDENCE  •  DECISIONS

# 9. LLM and MoE serving test track

Begin with prepared prompts and a small resident model. Keep retrieval, OCR, external tools, and live vector databases outside this track. A model family is not an ATMOS-support promise. Pin the actual revision, tokenizer, precision, quantization, and licensed artifacts before execution. [S3 §6]

| Experiment | Purpose | Vary after the control works |
| --- | --- | --- |
| Small resident dense model | Numerical/serving control | Input/output lengths, load, batching |
| Resident MoE | Isolate communication without forced storage misses | Valid TP/EP/replica layouts and placement |
| Tiered MoE | Test selected expert movement | Cache budget, routing trace, prefetch, path |
| Long context / paused session | Separate KV capacity and restore cost | Context, active sequences, KV layout, reuse |
| Mixed traffic and faults | Test service behavior | Bursts, cancellation, slow resource, recovery |

## Parallelism sequence

Start with one execution group. Compare valid TP, whole-expert EP, and smaller complete replicas only where the model fits. Then hold the logical group constant and change module/card/server placement. True expert tensor splitting is a separate capability check from attention TP plus EP. Do not multiply TP×DP×EP blindly; record the actual runtime’s rank groups. [S3 §§7–8; R9]

Advanced placement comes later: identical hot-expert replication, locality-aware owner placement, migration, predictive prefetch, and ring depth. Count extra copies, unused fetches, displaced KV, synchronization, and skew. Never alter the model’s selected experts simply to improve locality.

## Measurements

TTFT [s], TPOT [ms/token], end-to-end latency [s], offered and completed requests/s, output tokens/s, timing/quality pass rate, queue growth, unique weight bytes, KV allocation, exposed waits, and complete-system energy. Request rate is not concurrency; total parameters are not fetched bytes. [R8]

Gate: another engineer reproduces the control and can explain one bottleneck and one no-benefit region. A synthetic eight-request example does not establish a production p99 or actual model correctness. The supplied teaching scenarios are learning assets, not baseline measurements. [S10]

PLAN  •  EVIDENCE  •  DECISIONS

# 9. Vector and near-data processing track

For the E3.S product decision, first test a specific stage: candidate IDs and a query arrive; local vectors are gathered and scored; compact top-k results return. The database retains authoritative data, permissions, indexing, and lifecycle. [S2 §11.5; S5; S6]

| Stage | Owner / model responsibility |
| --- | --- |
| Query embedding and coarse retrieval | Existing service or frozen inputs; initially outside the timed device stage |
| Candidate selection and shard map | Host/engine supplies candidate IDs, filters, and snapshot version |
| Gather and scoring | Bridge models access sizes, outstanding slots, staging, and supported compute |
| Top-k and result merge | Device-local result plus explicit host/fan-out cost |
| Quality and freshness | Functional reference checks scores, allowed IDs, versions, deletion behavior |

Keep three workloads separate: exact vector rescoring; late-interaction/multi-vector matching; neural cross-encoder reranking. They need different inputs, operators, quality checks, and service budgets. TokenSim is not assumed to implement them all.

## Initial test variables

Candidate counts 1K/5K/10K as proposed ranges; actual dimension and precision; sequential versus scattered gathers; query rate and concurrency; read amplification; outstanding requests; cache budget; one versus multiple shards. Freeze values before comparisons. Use the strongest relevant DRAM, optimized NVMe, and GPU controls, including a resident control when the data fits. [S5 §7; S6]

## Two teachable calculations—not device predictions

If each useful byte is written into LPDDR and read back, a hypothetical combined 50 GB/s working-memory budget implies at most 25 GB/s for that staging pattern before other traffic.

For 32 outstanding 4 KiB reads with an assumed 20 µs service latency, the concurrency bound is 32×4,096 / 0.000020 ≈ 6.55 GB/s. More headline bandwidth need not fix insufficient outstanding reads. These are conditional bounds; the implementation and queue-credit rule require validation.

Gate: preserve numerical scores/top-k within the agreed rules, report latency including dispatch/merge, and show a material result or no-fit finding. Exact rescoring cannot retrieve a relevant item absent from the candidate set. Do not count simulated timing passes as accepted search goodput without correctness evidence.

PLAN  •  EVIDENCE  •  DECISIONS

# 9. Integration, calibration, and scope protection

## The partner route

The reviewed Bridge proposal reports block-level partner/RTL assets, not a complete ATMOS simulator. The stated February 2027 delivery is an internal planning assumption requiring confirmation. Do not copy partner-specific constants into a generic ATMOS profile without architecture approval. [S2 §§11.1–11.5]

| Work package | Acceptance evidence |
| --- | --- |
| Confirm artifact and rights | Current versus future scope, API, license, confidentiality, machine/CI requirements |
| Discover capabilities | Supported operators, address/queue semantics, timing units, unavailable features |
| Translate microtraces | Tiny deterministic commands with expected order, data, and failure behavior |
| Compare backends | Classify differences as bridge error, backend behavior, unsupported scenario, or unresolved input |
| Integrate safely | Process isolation, timeout, reproducible logs, version identity, named support owner |

Use supplied tests first. Do not build a full chip testbench or compiler as a prerequisite to every workload study. Reuse approved Sentinel/FlashKV concepts where they reduce effort, but do not rewrite the bridge in Rust/C++ before profiling demonstrates a need. [S1 §9; S2 §6]

## Calibration discipline

A measured RTX or OEM path calibrates that tested component, not unknown HBF/NPU behavior. Use held-out shapes/loads for error checks. Record mean and worst error over that tested range; set acceptable tolerances with the reviewer before evaluation. Paper-reported accuracy does not transfer automatically.

If a measured histogram includes queueing, do not add the same queue delay again. Preserve request arrival times, cancellations, failures, and unsupported cells. Do not sum overlapping busy times or per-stage p99s into request latency.

## Result package

Manifest; metrics; summary; sampled event timeline; assumptions with owner/source/date; configurations; plots; report; test reproduction instructions; decision or POC charter. Report NOT RUN / UNSUPPORTED / BLOCKED explicitly. [S2 §§8–9]

Release gate: a second engineer reproduces a reference case without your intervention; all critical inputs have provenance; a negative control exists; and there is a maintainer and clear allowed-claim boundary. A stopped workload can still produce useful requirements and prevent wasted investment.

EXECUTION ROADMAP  /  TARGETS SUBJECT TO GATES

# 10. Month 1: establish the hardware baseline

Illustrative period: 28 September–27 October 2026. Main outcome: explain the physical system correctly, agree scope, and produce one reproducible causal test. The original September tasks are carried forward after an audit—not assumed done. [S1 §10; proposed reset]

## First ten working days

| Day | Work | Artifact / owner interaction |
| --- | --- | --- |
| 1 | Meet Raj; confirm mission, three outcomes, authority, and working documents | One-page reset; source hierarchy; stakeholder introductions |
| 2 | Audit existing code/reports; identify reusable versus obsolete work | Status list: done with evidence / partial / not run; scoped backlog |
| 3 | Videos 1–3; ordinary server anatomy | Labeled board/CPU/RAM/storage map; mentor corrections |
| 4 | Videos 4–7; memory and PCIe | Socket/core/DIMM/link glossary; basic host topology |
| 5 | Videos 8–12; E3.S and switch picture | Three-layout map v0.1; five hardware questions; Friday note |
| 6 | Hardware walkthrough with mentor | Corrected lane/path map; unresolved values assigned to owners |
| 7 | Review current HBF/NPU/LPDDR inputs with Eric and relevant engineers | Versioned assumptions and capability ledger |
| 8 | Agree Bridge versus Rust/C++ baseline and minimum release | Architecture/scope decision; no duplicate implementation |
| 9 | Define profile, workload, result, evidence schemas | Device/topology/workload examples; unit conventions |
| 10 | Review with modeling/validation owners | Scope gate: staffing route, first microtrace, lab and partner actions |

## Week 2 decisions that must not remain implicit

Choose the lead E3.S workload, the measured-control access path, the current partner artifact, and the critical source revision. Determine whether the dedicated modeling support exists. If it does not, reduce scope now rather than miss an overloaded plan later.

## Immediate requests

Hardware map and supported link/port configuration; memory capacities and service ranges; NPU operator/precision coverage; command/buffer semantics; available lab measurements; partner scope/license/API; approved data and sharing rules. [S2 §13]

Do not promise a complete simulator at the first review. A correct hand-checkable resource test and reviewed architecture are the intended early proof.

EXECUTION ROADMAP  /  TARGETS SUBJECT TO GATES

# 10. Month 1: apply, test, and demonstrate

## Working days 11–20 and month close

| Day | Work | Artifact / review |
| --- | --- | --- |
| 11 | Repository, environment, CLI, and CI scaffold | Reproducible dry run and manifest |
| 12 | Capacity and unit calculations | Tests for bytes/bits, GB/GiB, weights, working-state reserve |
| 13 | One finite resource and deterministic event trace | Golden expected event order and queue wait |
| 14 | Add one shared path and buffer dependency | Demonstrate contention rather than fixed request latency |
| 15 | Peer review the causal example; complete videos 13–16 over available blocks | Friday demo; updated learning rubric |
| 16 | Obtain/read lab inventory, PCIe/NUMA map, versions | Baseline preflight or explicit access blocker |
| 17 | Freeze small dense/MoE and vector workload cards | Workload boundaries, inputs, operator needs, quality references |
| 18 | Observe a field/discovery discussion where available | One qualification card; no unsourced product promises |
| 19 | Reproduce the microtrace on a clean environment with another person | Reproduction log; fix missing instructions |
| 20 | Prepare monthly report and PM/architecture review | Top five gaps, next-month experiments, scope substitutions |

The remaining calendar days are for review, corrections, and buffer—not another large feature. If no lab is accessible, finish the request package and use an analytical control explicitly labeled as such; do not report a measurement.

## Month 1 exit checklist

Hardware owner reviews all three layouts. Critical parameters have source/owner/status. A small test shows both useful work and a reason for waiting. One baseline can be reproduced, or its access blocker is recorded. Raj agrees the next three outcomes, the lead workload, and staffing.

Expected learning level: explain CPU/RAM/storage, E3.S versus PCIe, switch versus connector, and local versus host traffic without notes. Explain the uncertain NPU/HBF path with notes and owner references.

## Change from the source schedule

The Bridge §13 first-month list is more ambitious than its 12–16-week roadmap and the current learning/support needs. This revision deliberately makes Month 1 a foundation gate, not a full five-workload MVR. Obtain Raj’s approval for that substitution. [S2 §§10, 13–14]

EXECUTION ROADMAP  /  TARGETS SUBJECT TO GATES

# 10. Month 2: build the smallest credible bridge

Illustrative period: 28 October–27 November 2026. Outcome: working resource models and one measured conventional path, where access permits. Keep the common core plus bounded LLM and vector examples; deepen only the approved lead. [S1 original Months 2–3; S2 §§7–10]

| Weekly package | Learning and engineering work | Output / review |
| --- | --- | --- |
| Week 5 | Study local memory/DMA; implement approved HBF, LPDDR, SRAM and transfer abstractions | Golden capacity, queue, staging and dependency tests; memory review |
| Week 6 | Add full-card/direct-E3.S/switched-E3.S profiles; test independent and communicating jobs | Local/host/peer bytes and shared-link contention report |
| Week 7 | Add one LLM/MoE trace and one vector query fixture; record unsupported operations | Small workload demonstrations and baseline plan; runtime review |
| Week 8 | Measure approved CPU/DRAM/NVMe or GPU path; retain a held-out test; add simple placement reason codes | First calibration comparison or explicit sensitivity-only report; Raj gate |

## Specific capabilities to demonstrate

A slower shared resource causes waiting; a larger queue does not invent bandwidth; an unavailable buffer prevents early consumption; unsupported routes fail visibly; idle/local execution does not consume the host link. Show one case where changing a headline specification does not improve the workload.

## Customer/OEM work

Observe or co-lead one discovery session; create a workload qualification card. Request the exact OEM topology and qualification conditions from one candidate plus an alternative when useful. Use an existing host first. Do not order an eight-accelerator system merely because the long-term diagram shows eight devices.

## Exit gate

Another engineer reproduces the bounded examples. Every critical parameter has provenance. The comparison identifies a useful next measurement. At least one control is measured if approved access exists; otherwise the report remains sensitivity-only and the limitation is visible. PM dispositions the most important requirements.

If support slips: ship the common resource model and one workload path. Do not sacrifice causality, correctness checks, or provenance to add every adapter.

EXECUTION ROADMAP  /  TARGETS SUBJECT TO GATES

# 10. Month 3: convert experiments into a decision

Illustrative period: 28 November–27 December 2026. Outcome: a credible study, not a broad uncalibrated platform. This is the three-month review; holidays and actual active engineering time affect the candidate-release date. [S1 original Months 3–4; S2 §§9–14]

| Weekly package | Work | Output / reviewer |
| --- | --- | --- |
| Week 9 | Freeze the strongest practical control and timing/quality boundaries; compare actual versus assumed paths | Baseline-parity checklist and controlled scenario matrix |
| Week 10 | Calibrate available components; use separate held-out shapes/load; identify sensitive unknowns | Error report by component/workload—not one global accuracy claim |
| Week 11 | Add selected fault/timeout/full-buffer cases and valid TP/EP or shard-placement alternatives | Deterministic policy report with reason codes and no-fit cases |
| Week 12 | Prepare partner contract, economic envelope, and lead POC charter; run clean reproduction | Review package and January priorities; internal integration acceptance |

## Three-month acceptance package

One system/topology map; versioned model/workload/device profiles; one measured control or blocked status; explanatory LLM and vector demonstrations within the agreed scope; at least one negative result; top five required hardware/software capabilities; partner input/return contract; qualified workload data request; and Raj’s next-stage decision.

## What “ready” does not mean

It is not proof of ATMOS token rates, final thermals, full model correctness, production Kubernetes support, or an OEM-approved device. A selected partner/RTL test may provide useful block evidence without proving the whole workload. [S2 §11]

## Resource decision at the gate

Continue only the workload whose requirement and product relevance are credible. Approve Month 4 hardening and a specific integration spike. If all results depend on unknown arbitrary timings, request the one measurement most likely to change the decision rather than building more charts.

Customer-stage goal: one internally qualified opportunity and a charter ready for joint review. A signed external POC depends on the customer and approvals; “ready for review” must not be reported as “active POC.”

EXECUTION ROADMAP  /  TARGETS SUBJECT TO GATES

# 10. Month 4: make the method usable by others

Illustrative period: 28 December 2026–27 January 2027. Outcome: supported reproduction and a realistic integration path. Build on the surviving Month 3 scope instead of adding a second major research program. [S1 original Month 4; S2 hardening phase]

| Package | Work | Proof |
| --- | --- | --- |
| 1 | Harden configuration validation, error messages, units, and capability checks | Invalid input and unsupported-operation tests |
| 2 | Select one runtime/backend interface with firmware and compiler owners | API, data ownership, timing, errors, cancellation, reset contract |
| 3 | Implement or hand off one proxy/adapter spike; repeat local/remote placement tests | Contract suite and topology-aware runbook |
| 4 | Clean-room reproduction; security/data review; customer workshop preparation | Independent reproduction, known limitations, owner acceptance |

## Placement and runtime depth

Add only the decision-relevant policies: capacity/admission, restore-versus-recompute for a justified state class, or expert/shard locality. Separate prefix/KV cache integration from model-weight loading; a KV-oriented framework does not automatically manage expert weights.

Study scheduler, KV layout, precision, and failure semantics alongside the selected runtime. Generic study of vLLM, SGLang, LMCache, model-import formats, and compiler boundaries now supports the actual interface decision rather than becoming multiple competing implementations. [S1 §§8–9]

## Release and ownership

Document installation, supported inputs, examples, calibration scope, error behavior, and how to add a profile. Assign a second maintainer/reviewer. A practical usability target is a reference run completed by a new engineer in about 30 minutes after prerequisites are installed; the Bridge proposal includes this as a v1 goal. [S2 §14]

No-hardware route: reproduce measured conventional controls and validate software contracts using explicit test doubles. Mark device-specific execution unvalidated. Do not call proxy success a passed physical DMA/reset test.

Gate: internally accepted handoff or owned adapter; one workshop-ready charter; next available measurement scheduled through the authorized owner.

EXECUTION ROADMAP  /  TARGETS SUBJECT TO GATES

# 10. Month 5: establish the joint baseline

Illustrative period: 28 January–27 February 2027. Outcome: customer/partner agreement on the problem and baseline, plus integration readiness for whatever partner artifact is actually available. February delivery is an assumption, not a promise. [S1 original Month 5; S2 §11]

| Package | Work | Output |
| --- | --- | --- |
| 1 | Conduct authorized workload/platform workshop | Sponsor, trace, quality/SLO, baseline, ownership, and data rules |
| 2 | Replay a customer-like workload internally, using synthetic/sanitized inputs where required | Instrumentation and quality report before comparative claims |
| 3 | Execute the conventional baseline with the operator; review bottleneck | Jointly understood baseline and metadata bundle |
| 4 | Review the ATMOS requirement hypothesis; confirm phase-2 tests | Comparative charter and agreed stop criteria |

## Partner readiness branch

Artifact available: confirm release, license, supported configurations and tests; run capability discovery and a tiny golden trace; compare expected ordering/data/timing; classify discrepancies before wider workloads.

Artifact delayed or narrower than expected: retain the bridge’s component model, profile interfaces, and conventional controls. Deliver the tested contract and missing-evidence list. Do not simulate “integration complete” by assigning future capability flags.

No external partner approved: complete an internal rehearsal and baseline package; report the opportunity at its real pipeline stage. Do not manufacture customer acceptance.

## OEM deliverable

Issue a configuration-specific readiness sheet: physical fit, lane/port map, power and sustained cooling, firmware/driver exposure, management, supported substitutions, and service procedure. Identify what is approved versus requiring engineering work. [S3 §§3–5]

Gate: both teams can reproduce the baseline or agree what blocks it; the next comparison tests a quantified hypothesis; no sensitive data or partner collateral is redistributed beyond the approved boundary.

EXECUTION ROADMAP  /  TARGETS SUBJECT TO GATES

# 10. Month 6: compare, decide, and hand off

Illustrative period: 28 February–27 March 2027. Outcome: an honest deployment/product decision and a maintainable package. Preserve the original calibration and POC closeout intent, but do not condition all progress on complete silicon arriving. [S1 original Months 6–7]

| Package | Work | Output |
| --- | --- | --- |
| 1 | Run agreed residency, memory-path, or retrieval configurations | Matched controls and comparable result bundles |
| 2 | Run selected locality, concurrency, topology, and negative controls | Fit/no-fit region and top unresolved sensitivities |
| 3 | Test approved failure/recovery behavior; update complete economics | Operational impact and cost/energy threshold |
| 4 | Joint or internal closeout; owner review; next charter | Proceed/iterate/pause/stop and requirements dispositions |

## Deliver by the six-month review

Technical: component-calibrated evidence where available; actual prediction error by tested envelope; correct result labels; one reusable integration/handoff; independent reproduction.

Product/OEM: two reviewed reference packages—typically one LLM-serving and one near-data retrieval configuration—with actual support status, boundaries, failure model, and economics. A reference package can explicitly be pre-silicon; do not call it a qualified production system.

Partner/customer: one jointly scoped evaluation and closeout if approvals/access allow, or a complete internal equivalent plus the external blocker and owner. Retain annual two-POC aspiration without inventing execution.

## Decision logic

Advance when a relevant region survives strong controls and uncertainty. Hold when one bounded missing input determines the answer. Stop/reposition when the baseline meets the goal economically, a required path is unsupported, or complexity erases value.

A numerical improvement target should be fixed in the charter with the decision owner. The proposal’s materiality examples are not ATMOS forecasts. Physical workload throughput, energy, thermals, or reliability can only be reported as measured after that exact system is tested. [S2 §§12–14; S6]

Learning milestone: lead the review without hiding unknowns; identify the right engineer, next test, and permitted conclusion for each disputed point.

EXECUTION ROADMAP  /  TARGETS SUBJECT TO GATES

# 10. Annual continuation: April–August 2027

Retain the original annual destination and work themes. The reset concentrates foundational work through March; the remaining five calendar months institutionalize the evidence and develop a second qualified adoption question. [S1 original Months 8–12]

| Month | Work packages | Exit evidence |
| --- | --- | --- |
| April | Execute approved POC 2 core comparisons; draft the reference template; adapt finance, sovereign/private, healthcare, RAG/agent, and industrial/edge packages where justified | POC 2 result or explicit blocker; five evidence-linked draft packages; at least two reviewers use sizing unaided |
| May | Package discovery/qualification tools; run SA/FAE workshop 1 on diagnosis and workshop 2 on evidence/TCO; observe users; disposition important requirements | Field Evaluation Kit v1; three observed users complete an exercise; top requirements have owners |
| June | Map runtime/OEM/ISV partnership needs; prepare approved ecosystem contribution; hold design-partner workshop; define mutual milestones | Partner action plan, approved contribution scope, and a shortlist/design-partner decision when externally agreed |
| July | Aggregate evidence; run selected multi-card/multi-node sensitivity; develop FY28 focus/broaden/partner/defer/stop options; pre-review disagreements | FY28 strategy with resources, evidence, risks, and stop conditions |
| August | Release or hand off tooling; approve five reference packages and field kit; archive stale claims; obtain cross-functional feedback; annual review | Maintainers, adopted artifacts, documented FY28 decisions, and next-year personal charter |

## Preserve evidence boundaries while broadening

A vertical package is a workload and deployment adaptation, not proof that every bank, hospital, or factory uses the same model or scale. Reuse measured mechanisms where applicable; mark new assumptions and untested environments. Approvals and data governance remain workload-specific.

A second POC should test a genuinely different adoption question—not repeat a favorable benchmark to count two. Avoid more than three active evaluations and more than one deep build branch without added support.

Annual success: the chain from customer problem to evidence to decision to adoption works without you personally performing every step. Report the original numerical targets and actual outcomes side by side; explain misses and changed priorities openly. [S1 §§12, 17]

PLAN  •  EVIDENCE  •  DECISIONS

# 11. Customer, partner, and economics workflow

Engage the organization operating the bottleneck: enterprise, managed service provider, ISV, hyperscaler, or OEM. Do not assume a named public company is an ATMOS prospect with an active relationship. The E3.S proposal’s initial practical combination is one integration partner, one workload owner, and one OEM/NPU feasibility path. [S6]

| Stage | Required work | Evidence to advance |
| --- | --- | --- |
| Signal → discovery | Confirm problem, sponsor, authority, and decision timing | Relevant meeting and workload owner |
| Discovery → qualified | Quantify trace, current stack, SLO, and plausible mechanism | Workload card and baseline/data request |
| Qualified → POC proposed | Sizing, requirements, responsibilities, data/IP and spend rules | Internally reviewed charter |
| Proposed → active | Joint agreement and reproducible baseline | Authorized execution and recorded gates |
| Active → decision | Controls, quality, failures, costs, and limits | Joint written disposition |
| Decision → design partner | Mutual integration/roadmap commitment | Approved milestones and ownership |

The original three qualified evaluations, two POCs, and one design-partner outcome remain annual goals, not assumptions about customer behavior. [S1 §11]

## Preparation and outreach

Bring the account objective, last actions, workload card, current architecture, approved claim list, three specific questions, and a desired next step. Ask first for a bounded technical workshop and sanitized trace—not a hardware purchase commitment.

## Economic evidence required

Record acquisition or rental basis, usable service capacity, utilization, reserve/replication, power at the agreed boundary, cooling/facilities, support, integration, maintenance, and migration. Calculate cost per accepted task/query/token only when quality and service requirements are matched. Existing hardware that cannot be retired is not immediate savings.

For product economics, request Finance-owned BOM/price/margin and development-cost recovery scenarios. Before quotes or performance exist, publish a price/performance requirement envelope, not revenue or savings. Reject a case that wins only by ignoring software, host resources, availability, or device lifecycle. [S6 §§10–12]

Pause when there is no sponsor, no usable workload detail, no relevant bottleneck, an unowned feature dependency, disproportionate support cost, or a demand for guaranteed unmeasured performance.

PLAN  •  EVIDENCE  •  DECISIONS

# 12. Metrics dashboard: measure useful progress

Review weekly and discuss trends monthly. The original annual outcome targets are retained; new milestone checks make them actionable. Counting documents or videos alone is insufficient. [S1 §12]

| Leading indicator | Working target | Evidence |
| --- | --- | --- |
| Protected deep work | At least 8 h/week; study/apply counts initially | Calendar blocks plus artifacts, not only bookings |
| Reproducible increments | 1 in Month 1; 2+/month afterward | Clean run, trace, configuration, reviewer |
| Architecture/runtime decisions | 2+/month after setup | Recorded option/disposition and owner |
| Evidence notes | Weekly | What changed, why, and next decision |
| Product backlog updates | 2+/month when evidence exists | Need, acceptance, owner, disposition |
| Field/user feedback | 1+/month after an artifact exists | Observed use and corrections |
| Customer sessions | 2–4/month once an active opportunity exists | Qualified outcomes—not meetings for the quota |

## Annual scoreboard

Three qualified evaluations; two completed POCs; one design-partner/shortlist outcome; five approved reference architectures; ten field users enabled and observed; ten requirements dispositioned; two reusable releases or handoffs; four executive decisions enabled. These are original aspirations, dependent on staffing and external readiness. [S1 §12]

## Quality indicators and definitions

Provenance coverage: all product-critical inputs and charts have evidence/source/owner. Reproduction: count attempted versus successful independent runs. Calibration: error by component, workload, and held-out region; no inherited universal accuracy claim. POC discipline: gates agreed before execution. Closure: due actions completed or explicitly replanned. Claim corrections: record withdrawals as risk avoided, not as failure to market.

For a learning skill, record 0–4 proficiency, evidence link, reviewer, and next exercise. For a project milestone, use not started / active / blocked / ready for review / accepted. Do not label “planned” as “green-complete.”

Monthly dashboard columns: metric; target; actual; evidence link; trend; blocker; next action; owner. Blank or unmeasured values remain blank/NOT RUN—never filled with illustrative numbers to improve the dashboard.

PLAN  •  EVIDENCE  •  DECISIONS

# 13. Personal development and visibility

The purpose of the learning reset is to increase engineering judgment, not to hide a gap. Build confidence by explaining a small system correctly, applying it to a test, and receiving correction. [S1 §13; new learning method]

## Internal first

Present one evidence review per month. Begin with the three-layout map or one causal microtrace; later present calibration, placement, and customer decisions. Ask for feedback from architecture, engineering, product, field, and validation at quarterly checkpoints.

Mentor one engineer or SA each quarter when you have a method you can teach. In the first quarter, pair-learning is appropriate: contribute software/reproducibility expertise while a hardware colleague supplies platform context.

## Impact log

For each important artifact, record the decision it enabled, who reused it, evidence quality, a limitation exposed, and the contribution of other people. “Created 20 slides” is weaker than “the platform team rejected an unsupported path before procurement.” Do not invent savings for avoided risk without Finance support.

## Quarterly conversation with Raj

Which outcomes create the most organizational value? Where am I operating below the role’s expectations? Which next-level scope should I own? Who needs to use my work directly? What evidence is needed for the next talent review? [S1 §13]

## External work—only after approval

Retain the original progression: generic memory-hierarchy methodology; reproducible evaluation methods; approved conference/workshop; runtime/community contribution; joint case study only with written permissions. Do not publish partner constants, customer traces, or unqualified performance claims.

## When you feel overwhelmed

Stop collecting new material. Choose the next physical object or interface you cannot explain. Watch its designated lesson, redraw it, ask one specific question, and save the corrected answer. Return to the weekly three outcomes. Do not use the learning gap as a judgment about your reliability; use the plan to make follow-through observable.

PLAN  •  EVIDENCE  •  DECISIONS

# 14. Risks, stop rules, and contingencies

The register extends the original risks with the new learning, scope, and hardware dependencies. Owners and trigger dates must be assigned in the working register. [S1 §14; S2 §12]

| Risk / trigger | Response |
| --- | --- |
| Hardware concepts remain unclear after the assigned lesson | Schedule a diagram review; narrow the next task; do not cover the gap with more slides. |
| Conflicting profiles or product priorities | Use the controlled source; record an architecture/scope decision and expiry for interim values. |
| No modeling support | Reduce to common resources and one workload adapter; rebaseline dates with Raj. |
| Partner artifact delayed, restricted, or narrower than expected | Continue conventional controls and bridge profiles; preserve tested adapter contract and explicit missing scope. |
| No credible NPU/HBF timing | Show required thresholds and sensitivities; do not publish a platform winner. |
| Simulator duplicates an available partner capability | Reuse/adapt it; stop redundant implementation after the scope review. |
| OEM cannot support proposed changes | Use another qualified fixture or maintain separate controls; never claim universal swapping. |
| Only the author can run the tool | Require a second-person reproduction, documentation, and maintainer before wider use. |
| Benchmark improves only under favorable assumptions | Add strong controls and no-fit cases; stop or revise the hypothesis. |
| Too many accounts or research branches | Limit three active major outcomes; new work displaces or receives added staffing. |
| Deep work falls below eight hours/week | Batch updates and decline optional forums; renegotiate workload. |
| Restricted material appears in a broad area | Stop redistribution; notify authorized owner; follow corporate process. |

## Non-negotiable stop conditions

Do not run unauthorized physical changes or destructive tests. Do not advance a numerical workload when correctness fails. Do not publish customer claims from teaching simulations. Do not promise a date controlled by an unconfirmed external dependency.

A stopped experiment can still close a product question. Preserve the trace, failed assumption, and recommendation so the organization does not repeat the same mistake.

PLAN  •  EVIDENCE  •  DECISIONS

# 15. Monthly review template

Complete at the final business-day review or the agreed checkpoint. Use one executive page plus linked technical evidence. [S1 §15]

Period: __________________  Review date: __________________
Owner / sponsor: __________________  Overall stage: __________________

| Review area | Fill in the decision-relevant facts |
| --- | --- |
| Outcomes | Which customer, product, or architecture decision moved? Who used an artifact? What was proved/disproved? |
| Hardware learning | Which concepts moved from recognition to explanation/application? Which engineer reviewed the result? |
| Measured evidence | Exact platform, configuration, test boundary, and raw result link |
| Modeled evidence | Model/backend version, assumptions, sensitivity, and permitted conclusion |
| Quality and calibration | Reproduction attempts/results; numerical correctness; held-out error; remaining gaps |
| OEM/partner status | Current artifact/access versus promised or expected delivery; supported versus unqualified configuration |
| Customer/product movement | Actual pipeline stage and requirement dispositions, not speculative account interest |
| Time and spend | Planned/actual allocation; approved spend and remaining ceiling; scope pressure |
| Claims | Added, changed, withdrawn, or blocked for external use |

## Portfolio disposition

Continue: __________________  Stop: __________________
Start instead: __________________  Delegate/handoff: __________________

## Next-month contract

Outcome and acceptance evidence: __________________

Outcome and acceptance evidence: __________________

Outcome and acceptance evidence: __________________

Explicit non-goals: __________________
People/access/decision required: __________________
Owner and due date for each blocker: __________________

## Sponsor decision

Advance / hold / rescope / stop: __________________
Rationale and evidence link: __________________
Next review: __________________

PLAN  •  EVIDENCE  •  DECISIONS

# 16. Weekly planning template and first-week example

Use the original one-week contract, now explicitly linking learning to applied work. Do not add tasks merely to fill every row. [S1 §16]

Week of: __________________
This week succeeds if: ______________________________________________

| Priority | Deliverable and evidence | Consumer / due | Status |
| --- | --- | --- | --- |
| 1 | __________________________ | ______________ | __________ |
| 2 | __________________________ | ______________ | __________ |
| 3 | __________________________ | ______________ | __________ |

Protected blocks: __________________  Lessons and application: __________________
Pre-reads / reviews: __________________  Customer follow-up: __________________
Risk to escalate: __________________  Work deferred: __________________

## Filled example: first week of the reset

| Priority | Deliverable | Consumer and finish test |
| --- | --- | --- |
| 1 | Learning lessons 1–3, 5, 7, followed by a labeled ordinary-server map | Hardware mentor can identify and correct the explained parts. |
| 2 | Three ATMOS layouts plus source/unknown register | Raj agrees which configuration and document guide the next work. |
| 3 | Existing-code audit and first microtrace specification | Modeling reviewer can see what will be reused and the expected event sequence. |

Defer: new winner heatmaps, large-model downloads without a need, unapproved server changes, and a full runtime rewrite.

## Friday result

Evidence produced: __________________
Decision moved and owner: __________________
Artifact reused/reproduced by: __________________
Surprise/failure and response: __________________
Claim changed: __________________
First action next Monday: __________________

A blocker is complete only when its impact, owner, and requested action are recorded. “Still researching” is not a sufficient weekly close when the same uncertainty persists.

PLAN  •  EVIDENCE  •  DECISIONS

# 17. Definition of a good year

Retain the original chain of evidence:

Customer problem → quantified workload → reproducible baseline → architecture hypothesis → controlled evaluation → product decision → deployable reference → field or customer adoption. [S1 §17]

## What success looks like in this revised plan

By one month, you can explain the hardware honestly and know which engineer confirms each unknown. By three months, a small repeatable evaluation changes a decision. By six months, others can use the method and a partner/OEM path is either progressing or explicitly blocked for a known reason. By August, the capability survives without you personally running every step.

## Final readiness checklist

| Area | Evidence to show |
| --- | --- |
| Understanding | Reviewed three-layout map; correct local/host/peer path explanation |
| Engineering | Source-linked profiles; deterministic tests; meaningful negative controls |
| Evidence | Measured/model/partner labels; calibration limits; no unsupported performance cells |
| Adoption | Workload owner, actual pipeline stage, supported interface and OEM requirements |
| Operations | Maintainers, reproduction, safe failure behavior, support boundaries |
| Influence | Requirements dispositioned, executive decisions, and reusable field tools |

## The operating agreement to confirm

Raj confirms priorities, sponsor access, and staffing. Architecture owners approve critical inputs. Validation accepts the evidence method. Product/Finance own commercial assumptions. You own the work’s coherence, reproducibility, communication, and follow-through.

What this plan does not require: becoming an expert in every hardware discipline immediately, promising positive ATMOS results, or measuring yourself by the volume of documents produced.

What it does require: keeping commitments small enough to finish, asking precise questions, recording uncertainty, accepting negative evidence, and making the next decision easier for the team.

For the next workday, start with Lesson 1 and the first-week outcome contract. The rest of the plan is there to prevent the next learning gap or project branch from taking over the whole calendar.

WORKING REFERENCE

# Appendix A. Hardware and serving vocabulary

Use this as a recognition aid, not a substitute for the actual device specification. The public references explain general hardware; the internal sources define proposed ATMOS roles. [R1–R4; S2–S4]

| Term | Meaning to retain |
| --- | --- |
| Server / chassis / motherboard | Complete machine / enclosure / main connection board |
| CPU package / core / socket | Installed processor / instruction-executing unit / physical CPU connection |
| RAM / DRAM / DIMM | Working-memory role / memory technology / physical memory module |
| Storage / NAND / NVMe | Persistent-data function / flash medium / storage command interface |
| PCIe generation / lanes | Rate family / number of parallel link lanes; neither is application throughput |
| Endpoint / root port | Attached device interface / host-side PCIe port |
| Switch / uplink | Transaction-routing component / connection toward the host or next hierarchy |
| Retimer / bifurcation | Signal restoration / splitting supported host lanes into smaller ports—not switching |
| AIC / riser | Add-in circuit card / assembly connecting and positioning cards in the chassis |
| E3.S / bay / backplane | Device form factor / insertion position / board behind the devices |
| MCIO | Connector/cable system; a cable does not perform switch routing |
| NUMA | Host CPU/memory locality; separate from actual PCIe peer routing |
| DMA / interrupt | Engine-managed data movement / notification mechanism |
| NPU / HBF / LPDDR / SRAM | Neural compute / proposed persistent capacity / writable working memory / small on-chip working storage |
| NoC / HIM / CSC | On-chip network / internal module labels whose precise roles require the approved specification |
| BIOS/UEFI / BMC | Platform startup firmware / server management controller |
| NIC / RDMA | Network interface / supported remote-memory-transfer mechanism |
| TP / EP / PP / replica | Tensor splitting / expert distribution / layer stages / complete logical serving copy |
| KV / prefill / decode | Attention state / prompt processing / incremental response generation |
| Request rate / concurrency / batch | Arrivals per time / unfinished requests at a defined boundary / work grouped for execution |
| TTFT / TPOT / goodput | First-token latency / average time per output token under a defined convention / useful completed work meeting agreed checks |
| DES / profile / calibration | Event-based virtual-time model / inputs describing a configuration / adjustment and error checking against evidence |

Do not use “TPS” without stating tokens or transactions, input or output, per-user or aggregate, and the quality/latency boundary. Do not treat total MoE parameters as per-token traffic or label power in watts as energy per token. [R8; S9]

WORKING REFERENCE

# Appendix B. Reusable technical worksheets

## Hardware profile: one sheet per configuration

| Field | Record value, source, status, and owner |
| --- | --- |
| Identity | Profile ID/date; source revision; full card, direct E3.S, or switched E3.S |
| Host and devices | CPU/DIMMs; firmware/OS; device count and exposure |
| Local execution path | HBF destination; staging; memory capacities and reserves |
| Interconnect | Device links; switch/cables; shared host uplink; supported peer route |
| Operation | NUMA placement; power/cooling; reset/management; qualification |
| Unknowns | Top three missing inputs, owner, and requested measurement |

## Experiment contract

Decision and hypothesis: __________________________________________
Disconfirming result: __________________________________________
Workload/model/data version: _____________________________________
Changed variable / fixed controls: _________________________________
Timing and quality boundary: _____________________________________
Expected golden behavior / backend: ______________________________
Pass, hold, and stop gates agreed before execution: __________________

## Result record

| Required item | Record |
| --- | --- |
| Evidence and identity | Analytical / simulated / calibrated / functional / physical; versions and seed |
| Metric and sample | Primary KPI, units, count, repetitions, and uncertainty |
| Correctness and failures | Data/output check, timing pass, errors, unsupported cells |
| Interpretation | Dominant wait, calibration envelope, what changes the decision |
| Review and use | Evidence link, reviewer, permitted claim, next action |

Units checks: 8 bits = 1 byte; GB and GiB differ; bandwidth needs endpoints and direction; p99 needs sufficient representative observations. Aggregate capacity is not uniformly accessible memory. A stable-system rate×mean-duration relation does not convert peak concurrency or p99 into throughput. [R8; S2 §8]

WORKING REFERENCE

# Appendix C. What changed from the original plan

This document preserves the original structure and annual goals while revising sequence, scope, and dependencies. It is not a claim that any draft has been formally superseded. Raj and the domain owners must approve the working baseline.

| Original section | Retained | New context incorporated |
| --- | --- | --- |
| 1. North star | Workload → evidence → adoption | Product, physical topology, and evidence decisions separated |
| 2. Success contract | August outcomes and operating rules | 1/3/6-month capability and artifact gates |
| 3. Time budget | Six portfolios; three active outcomes | Temporary learning allocation; supported and solo routes |
| 4. Everyday system | Daily blocks and weekly synthesis | Applied learning, recovery rule, protected scope |
| 5. Stakeholders | Sponsor and engineering map | Hardware mentor, modeling reviewer, partner liaison |
| 6. Meetings | Seven playbooks and explicit outcomes | Raj reset and physical-path questions |
| 7. Artifacts | Registers, memos, reports, references | Source arbitration and draft-conflict control |
| 8. Curriculum | GAIA, runtime, deployment, ecosystem depth | Level-zero videos, exercises, 0–4 proficiency rubric |
| 9. Code/POCs | Harness, policy, integration, evidence ladder | Bridge scope, OEM/NUMA, HBF-active retrieval, partner tests |
| 10. Roadmap | Baseline, POCs, calibration, field adoption | Rebased near term; first-month overload removed |
| 11. Pipeline | Qualification through design partner | Operator/ISV/OEM engagement and full economics |
| 12. Dashboard | Leading, outcome, and quality measures | Evidence-linked skills, support/blocked status |
| 13. Development | Mentoring, feedback, approved external work | Pair-learning and confidence through application |
| 14. Risks | Delay, ambiguity, bias, dependency, overload | Learning, duplicate implementation, OEM compatibility |
| 15–16. Reviews | Monthly and weekly templates | Hardware/partner/evidence fields and first-week example |
| 17. Good year | Reusable decision capability | Explicit ownership and sustainable follow-through |

Scope reconciliation: recommend Python/SimPy bridge first, optional TokenSim for LLM, measured controls, and selected partner adapters [S2]. Keep the Rust/C++ proposal as an alternative [S8]. Retain LLM-only versus RAG separation [S3], while prioritizing HBF-active E3.S retrieval only after Raj resolves the lead-product decision [S2 §11.5]. CXL is a learning/optional control topic, not reintroduced into the customer’s RTX-versus-ATMOS chart by default.

WORKING REFERENCE

# Appendix D. Source register and technical references

## Internal source basis

| ID | Source and use |
| --- | --- |
| S1 | shailesh-12-month-operating-plan(3).md — all 17 sections, annual goals, stakeholder assumptions, routines, roadmap, and templates. |
| S2 | ATMOS_Bridge_Emulator_Implementation_Proposal.docx — reviewed 22-page draft; implementation choice, evidence, staffing, partner boundaries, and §11.5 priorities. |
| S3 | ATMOS_HBF_OEM_Platform_and_LLM_Evaluation_Plan_Draft.docx — 21-page OEM, replacement, NUMA, workload, and parallelism plan. |
| S4 | ATMOS_E3S_Product_and_Workstream_Proposal(1).docx — one-module E3.S versus full-card product, interfaces, engineering responsibilities. |
| S5 | ATMOS_E3S_HBF_Use_Case_Strategy_and_POC_Roadmap(1).docx — near-data workloads, memory-path requirements, and retrieval tests. |
| S6 | ATMOS_E3S_Executive_Product_and_Partner_Proposal(1).docx — buyer, partner, full-cost economics, and adoption framework. |
| S7 | IMG_1041.jpeg — supplied passive-backplane / MCIO / separate-switch-card illustration; unconfirmed implementation details. |
| S8 | PROPOSAL.md — previously discussed Rust/C++ digital-twin design; reusable concepts, not assumed approved alongside S2. |
| S9 | README_ATMOS_Final_Deck_Review_and_Slides_04-12(1).md — evidence/axis/claim corrections. |
| S10 | ATMOS_Two_Worked_Scenarios.md and package — educational replay, not TokenSim or physical ATMOS measurements. |

## Public references

R1: Dell R770 service manual. R2: SNIA form factors. R3: Linux PCI peer-to-peer DMA. R4: NVIDIA GDS design guide.

R5–R7: lesson 17 networking, lesson 18 MoE, lesson 19 NCCL. R8: NVIDIA benchmarking fundamentals. R9: vLLM parallelism and EP. R10: Kubernetes architecture. V1–V16: direct lesson and publisher links in §8.

Source status: source files are supplied planning material, not independently verified releases. New prioritization, allocations, checkpoint dates, exercises, and scope substitutions are this revision’s recommendations. Use current controlled sources before external claims or physical changes. Public link access is described in §8; no claim of complete video playback review is made.