ARCHITECTURE • CUSTOMER ENABLEMENT • PARTNER DELIVERY

# ATMOS

# Ecosystem Engagement &
Product Readiness Plan

A phased route from direct E3.S workers to a qualified integrated model-serving platform

A — DIRECT E3.S     /     B — SWITCHED E3.S     /     C — INTEGRATED CARD

| A • Start with local work | B • Qualify the fabric | C • Qualify the complete group |
| --- | --- | --- |
| One worker, then 4–8 direct-attached workers. Prove useful HBF access and a maintained software boundary. | Eight modular workers behind a qualified switch. Add peer DMA or Gen6 only when a workload earns it. | Eight building blocks inside one card assembly. Validate cooperating models, packaging and complete-group recovery. |

| 128 GB | 200 GB/s | 8–16 GB |
| --- | --- | --- |
| Nominal HBF target per module. Planning application budget: 100 GB. | Local HBF read target per module. Not PCIe bandwidth or achieved service rate. | LPDDR target per module. Working memory is separate from HBF capacity. |

DECISION REQUESTED Approve one readiness program with phased release gates, a small set of direct engineering relationships, and named owners for every indirect dependency. Start future-phase architecture engagement now; do not promise future-phase features on Day 1.

| Document control | Status |
| --- | --- |
| Version / date | v1.0 • 27 September 2026 |
| Steward / audience | Proposed steward: Shailesh Pilare. Sponsor, architecture, product, firmware, runtime, OEM, validation and account teams. |
| Release status | INTERNAL REVIEW DRAFT. New nomenclature and recommendations require approval. No ATMOS performance, supplier award or customer commitment is established. |
| Planning horizon | 2028 silicon availability is program-owner planning context, not a production-release promise. |

Basis: supplied Master v3 [I1], Bridge implementation proposal [I2], Executive product/partner proposal [I3], current program-owner direction [U1], and dated primary-source research [R1–R36].

READ FIRST • DECISIONS AND NOMENCLATURE

# Executive recommendation

Deliver the simplest supportable ATMOS service first. Use A to establish local device value, B to establish whether shared connectivity and peer routing improve the system, and C to deliver a qualified integrated execution group. Reuse the same device contract, evidence system and customer acceptance method.

| New name / delivery phase | Previous Master name | Meaning |
| --- | --- | --- |
| A • Direct-attached E3.S | Old B | Independent E3.S NPU + HBF + LPDDR workers. |
| B • Switched E3.S | Old C | One family: B1 separate switch AIC; B2 OEM-integrated switch. |
| C • Integrated ATMOS card | Old A | Eight compute/memory building blocks inside one accelerator card. |
| Composition / scale-out | Old E / F | Deployment patterns across qualified A/B/C; not fourth and fifth silicon phases. |

## First-preference engagement sequence

Direct now: the authorized anchor customer, Tenstorrent, Dell platform engineering, Microchip Switchtec applications engineering, and Sandisk’s device/firmware/runtime owners. Run a bounded Broadcom PEX89048 alternative review in parallel. Engage one board partner and one retrieval integration owner—not every candidate at implementation depth.

Software enablement: use Canonical/Ubuntu as a lab-support candidate subject to Tenstorrent compatibility; use Red Hat/OpenShift as the primary enterprise orchestration discovery candidate when it matches the customer platform. Kubernetes and vLLM upstream remain tracked dependencies, not substitutes for a support vendor.

Deferred commercial commitment, early architecture work: B2 platform integration, native Gen6, device P2P, C card design and grouped execution. Their hardware requirements may need decisions before A ships.

WHAT IS ACTUALLY KNOWN The program owner reports active Tenstorrent engagement for runtime and emulators. The source describes an anchor direction involving Google, but supplies no signed scope or adoption evidence. All other named organizations in this plan are proposed counterparties, public reference platforms, or conditional suppliers—not claimed active partners.

Naming change is explicitly requested by the program owner [U1]. Portfolio scope: [I1, pp.2,4,8–11]. Supplier priorities are new recommendations; technical basis and sources appear on pp.16–22 and 30–33.

NAVIGATION • EVIDENCE • TIME

# Three delivery phases, parallel engagement

A/B/C name hardware offerings and their recommended release progression. Evaluation readiness, device readiness and production readiness are separate states within each phase. A pre-silicon demonstration is not an A product release.

| Readiness state | Deliverable | Permitted conclusion |
| --- | --- | --- |
| E • Evaluation | Trace replay, CPU/GPU reference, analytical/DES profiles and assumptions. | Requirements and sensitivity; reference-platform measurements only. |
| D • Device developer kit | Actual supported endpoint or card, firmware/driver, kernels and diagnostics. | Function and measured paths of that exact build. |
| P • Production service | Qualified OEM BOM, supported runtime/packs, installation, recovery and support. | Customer service claims within the tested envelope. |

## Release order does not dictate when work starts

Before silicon, build the A workload contract and baseline while opening B switch/OEM reviews and C packaging/runtime requirements. At usable silicon, qualify A-D and A-P. Promote B and C only when their additional gates pass. A and B remain sellable configurations; customers do not have to migrate through every phase.

Treat 2028 as the current silicon assumption. Separately confirm tapeout/design-freeze dates, first silicon, engineering samples and production readiness. The older February 2027 partner-emulator milestone is an assumption to revalidate with Tenstorrent, not a schedule commitment.

| Evidence label | Use throughout this plan |
| --- | --- |
| SOURCE TARGET | Unreleased ATMOS value from supplied documents; engineering approval still required. |
| PUBLIC FACT | A dated vendor publication; does not establish ATMOS compatibility. |
| PROPOSED / ANALYTICAL | A recommended requirement, experiment or calculation—not measured capability. |
| MEASURED / QUALIFIED | Reserved for a traceable physical result or approved release; none supplied for ATMOS. |

## Reading routes

Device, phase and workload envelopes • pp.4–11

Direct and indirect engagement ownership • pp.12–15

Named vendor choices and engineering scope • pp.16–23

Execution, gates and leadership decisions • pp.24–29

Source register and verification boundaries • pp.30–33

Evidence hierarchy and separate release packages: [I1, pp.3,27,33,37]; partner scope and timing: [I2, §§3,11]. This plan does not modify an approved silicon specification or signed statement of work.

SHARED FOUNDATION • SOURCE TARGETS

# Device specification ledger

These values apply to the proposed building block, not automatically to every SKU. Freeze an owner, revision, unit, operating condition and validation method before a value becomes a release requirement.

| Parameter | Per module / E3.S direction | Eight-module / eight-device sum |
| --- | --- | --- |
| HBF nominal capacity | Up to 128 GB. Usable capacity TBD. | 1,024 GB nominal when all eight match. |
| Application HBF budget | 100 GB proposed for planning; includes the chosen reserve policy. | 800 GB planning allocation. Not the deck’s separate 900 GB/card scenario. |
| Local HBF reads | 200 GB/s source target; useful random/gather service unknown. | 1.6 TB/s local sum, only under simultaneous local work—not one shared port. |
| HBF writes / access | Per-module sustained writes and read granularity need confirmation. | Source card table: 64 GB/s writes and 4 KB minimum access; do not allocate per module by assumption. |
| LPDDR | 8–16 GB; 50 GB/s source direction, combined versus directional scope unresolved. | 64–128 GB distributed capacity; not a coherent workspace. |
| SRAM | Up to 32 MB SoC-local direction; NPU SRAM separately identified. | Do not sum caches or independently owned SRAM without an approved address map. |
| Compute | 64 TOPS/TFLOPS mixed INT8/FP8 source label. | 512 aggregate label; not an effective operator rate or token/s figure. |
| E3.S PCIe | Gen5 or Gen6 x4 candidate. Endpoint generation not frozen. | A: host lanes per device. B: explicit shared switch topology. |
| Integrated C links | Source image: internal Gen6 x4 per module. | Source image: host Gen5 x16. Changing this requires a new approved card design. |
| Power / mechanical | E3.S versus 2T, connector, cooling and accelerator power TBD. | C has a ~200 W-class source target; switch and board overhead must fit the complete budget. |

THE 200 GB/S TARGET MUST REACH USEFUL COMPUTE If each useful byte is written and then read through a combined 50 GB/s LPDDR interface, that staging pattern alone limits delivery to 25 GB/s before other traffic. Resolve the HBF → controller/NoC → LPDDR or bypass → NPU path before discussing throughput.

SOURCE TARGETS: [I1, pp.5–6,16]; conditional staging calculation: [I3, §8 and Appendix A]. E3.S physical precedent [R33] does not qualify ATMOS power, hot removal or PCIe support.

PHASE A • NEW A = OLD B

# A — Direct-attached E3.S workers

Release objective: a useful, recoverable local service on one ATMOS E3.S device, then a qualified 4–8-device direct-attached population. Gen5 x4 is the proposed first fixture; the silicon team must confirm the actual endpoint mode.

Host lane group → one x4 ATMOS worker; repeat per qualified bay

| Scope | Phase A release candidate | Explicitly deferred |
| --- | --- | --- |
| Workloads | P0 local memory-path tests; P1 fixed-candidate scoring. One small dense/MoE model only after kernel and quality gates. | Fine-grained cross-device expert parallelism; arbitrary models; universal GPU replacement. |
| Capacity / paths | 128 GB nominal HBF, 100 GB planning budget and 8–16 GB LPDDR per worker. Gen5 x4 ≈15.75 GB/s coded ceiling per direction before transaction overhead. | Treating 200 GB/s HBF as PCIe bandwidth; coherent pooling. |
| Scaling | 1 → 4 → 8 independent workers. Eight direct x4 paths consume 32 host lanes, if physically routed. | Automatic eightfold query throughput for a query requiring every shard. |
| Software | Sandisk command/driver contract; selected TT primitive backend; one maintained scorer boundary; whole-worker allocation. | Production serving support from a simulator callback alone. |
| Operations | Safe drain, reset, versioned packs/snapshots, health, error reporting, installation and rollback. | Unqualified surprise removal, fractional sharing and same-device dual-fabric failover. |

## Direct engagement deliverables

Customer + account owner: an authorized trace, quality/freshness rules and a conditional evaluation agreement. Tenstorrent: one primitive/model capability matrix and emulator/functional test interfaces. Dell + Sandisk platform team: an exact direct PCIe path, bay power/cooling, BIOS/BMC and reset map. Runtime/OS partner: a pinned supported build, not just a container that starts.

## Exit evidence

One independent engineer can install the package, reproduce numerical results, run the selected R1 or L1 profile, and recover from a declared device failure. Release throughput is the measured accepted rate under the unchanged quality and latency contract, not a target extrapolated from bandwidth.

PARALLEL WORK ALLOWED During A, engage Microchip/Broadcom for B and Tenstorrent/card engineering for C. Those studies must not add Gen6 or P2P as prerequisites for the first local retrieval proof.

Phase content derived from [I1, pp.8,27–34] and [I3, §§4,7,9,17]. Phase allocation and Gen5-first fixture are new recommendations. PCIe basis: [R1,R11].

PHASE B • NEW B = OLD C

# B — Switched E3.S family

Release objective: the same modular workers with a qualified shared fabric. B1 places the switch on an add-in card; B2 integrates it into the OEM motherboard, riser or active backplane. B2 is not a mandatory successor to B1.

Host x16 → switch → 8 × x4 E3.S ATMOS workers

| Capability | B baseline | B extension, separately gated |
| --- | --- | --- |
| Links | Gen5 x16 host; eight Gen5 x4 endpoint paths. One sufficiently sized switch can connect all eight. | Gen6 host uplink and/or endpoint links only with exact switch, endpoint and OEM support. |
| Capacity / local reads | 1,024 GB nominal HBF / 800 GB planning budget; 64–128 GB distributed LPDDR. Up to 1.6 TB/s target sum of local reads. | No increase in per-worker memory/compute from adding a switch. |
| Host traffic | ~126 GB/s aggregate Gen5 downstream coded ceiling versus ~63 GB/s upstream; nominal 2:1 concentration. | Mixed-generation payload measurements; no raw-rate claim of guaranteed nonblocking service. |
| Workloads | Larger retrieval corpus, independent small-model replicas, P2 multi-vector scoring after primitive proof. | Cooperating MoE subgroup only after peer path, runtime, per-rank fit and complete-group recovery pass. |
| P2P | Not required for host fan-out / compact result merge. Maintain host-coordinated reference. | ATMOS peer apertures, DMA, ordering, security and software lifecycle must all work. |
| Availability | Replicate required data/model service across independent nodes or declared domains. | Two switch chips alone are not HA; dual-port same-device failover is separate architecture. |

## What the switch must earn

With eight existing bays, B still holds eight devices. Its value is lower host-lane consumption, potential local peer routing and a manageable fabric. The saved 16 host lanes have value only if the OEM routes them to a usable NIC, GPU, storage or second fabric connection. Price the switch, cabling, power, support and shared-failure exposure against that benefit.

## B release gate

Compare A and B at the same worker count, workload and quality. Test all workers active, loading/updates, uplink saturation, valid peer transfers, isolation and switch loss. Promote B only when the accepted service or platform economics justify the extra fabric.

Topology and service boundaries: [I1, pp.9–13,24,31–32]. Proposed B extensions are not current ATMOS capabilities. Switch/peer mechanisms: [R1,R4,R12].

PHASE C • NEW C = OLD A

# C — Integrated ATMOS card

Release objective: a complete, qualified cooperating-model group in an integrated card assembly. C contains eight compute/memory building blocks, LPDDR, a switch and board infrastructure; it is not eight enclosed E3.S devices mounted on a card.

Host x16 → on-card switch → 8 internal module links

| Area | Current source direction | Required C acceptance |
| --- | --- | --- |
| Memory / compute | 1,024 GB nominal HBF; 64–128 GB distributed LPDDR; 1.6 TB/s parallel local-read target sum. | Approved usable per-rank placement, buffers, runtime reserve and supported operators. |
| Fabric | Internal Gen6 x4 per module; host Gen5 x16 in source image. | Exact chip/port map, native Gen6 signal path, peer DMA and concurrent traffic measurements. |
| Power / packaging | ~200 W-class card target; dimensions, slot thickness and auxiliary power unresolved. | Full BOM power budget, sustained thermals, retention, spacing and approved service flow. |
| Workloads | Large MoE group and bounded multi-device execution; retrieval/replicas remain possible if independently exposed. | One pinned Qwen3-235B-A22B or other agreed model first; larger DeepSeek-V3 case only after fit and runtime proof. |
| Beyond one card | One card is not a universal large-model capacity boundary. | Explicit cross-card transport, synchronization, placement and group recovery; no free pooling. |
| Product support | Card-level replacement and supported device/group identity. | Recover the complete service after module/card failure; provide customer-visible limitations. |

## Engagement begins before A release

Sandisk card/hardware engineering, Tenstorrent compiler/runtime and the selected switch vendor must agree peer visibility, command queues, reset scope and internal fabric requirements before silicon/card design freezes. Dell accelerator-platform engineering and the selected board/ODM partner review C mechanics, power and service ownership in parallel.

DO NOT INHERIT A FALSE BANDWIDTH ASSUMPTION The source C arrangement—eight Gen6 x4 internal links with a Gen5 x16 host link—has roughly a 4:1 nominal host-bound bandwidth mismatch, not the 2:1 same-generation B example. Local peer traffic can avoid that host link only when the full path is supported. A Gen5 lab surrogate does not validate the native Gen6 C card.

SOURCE TARGETS: [I1, pp.5–7,14–17]. Integrated C replaces old A only by the requested naming change. Gen6 behavior: [R10,R11,R36]; group/runtime work is proposed, not delivered.

COMPARE LIKE WITH LIKE • CALCULATED CEILINGS

# Capacity and connectivity by phase

| Metric | A • 8 direct workers | B • 8 switched workers | C • 8-module card |
| --- | --- | --- | --- |
| Nominal / study HBF | 1,024 / 800 GB | 1,024 / 800 GB | 1,024 / 800 GB* |
| LPDDR sum | 64–128 GB distributed | 64–128 GB distributed | 64–128 GB distributed |
| Local read target sum | 1.6 TB/s | 1.6 TB/s | 1.6 TB/s |
| Host connection case | 8 × Gen5 x4 | 1 × Gen5 x16 | Source: 1 × Gen5 x16 |
| Host coded ceiling / direction | ~126.0 GB/s total across paths | ~63.0 GB/s shared | ~63.0 GB/s shared |
| Endpoint/internal case | Gen5 x4 each | Gen5 x4 each | Source: Gen6 x4 each |
| Front E3.S bays used | 8 compatible positions | 8 compatible positions | 0 for the on-card modules |
| Expansion slot / assembly | OEM lane routing decides | B1 consumes switch AIC position | One qualified accelerator position |
| Memory is coherent? | No assumed pooling | No assumed pooling | No assumed pooling |

* C uses the common 100 GB/module study allocation here. The older 900 GB/card case is a separate allocation, not an additional capacity. [I1, pp.5–6,13].

## Gen5 and Gen6: keep the accounting basis visible

| Link, per direction | Gen5 after 128b/130b coding, before TLP overhead | Gen6 raw-rate ceiling, before FLIT/FEC/TLP overhead |
| --- | --- | --- |
| x4 | 15.75 GB/s | 32 GB/s |
| x8 | 31.51 GB/s | 64 GB/s |
| x16 | 63.02 GB/s | 128 GB/s |

Gen6 uses 64 GT/s PAM4 with FLIT/FEC/CRC rather than Gen5’s 32 GT/s NRZ scheme. Eight Gen5 x4 endpoints behind a Gen6 x16 host link are approximately rate-matched at the headline level, but the different overheads, packet mix and switch limits still determine usable payload. Do not promise exact nonblocking throughput from this arithmetic.

A switch does not add physical bays or expose unused CPU lanes automatically. For a GPU under the same fabric, a minimum lane-budget example is 16 CPU + 32 E3.S + 16 GPU = 64 switch lanes; 48- and 52-lane parts cannot supply that exact map. Port grouping must also be supported.

Calculations from stated widths/rates [R1,R11]; ATMOS topology targets [I1, pp.6,13,44]. No values in these tables are measured ATMOS payload rates.

QUALIFICATION PROFILES • PROPOSED DEMAND, NOT ACHIEVED THROUGHPUT

# Workload contracts by phase

The profiles below make the test program concrete. They are proposed offered loads and acceptance objectives, not customer promises or published ATMOS performance. Freeze quality, trace, packet/read mix and full-service boundaries before testing.

| Profile / first phase | Work and resource demand | Load sweep / proposed latency objective |
| --- | --- | --- |
| R1 • Candidate scoring A → B | 1,024-dimensional FP16 vectors; 5,000 total candidates/query; top-100. 10.24 MB useful reads/query. At 1,000 QPS: 10.24 GB/s useful, or 20.48 GB/s with assumed 2× read amplification. | A one-worker sweep: 100 / 250 / 500 / 1,000 QPS. P99 scorer ≤20 ms at admitted load; numerical/order equivalence. |
| R1 scale-out B | Eight 100 GB study shards = 800 GB distinct corpus. At 4,000 global QPS: 40.96 GB/s useful aggregate; 5.12 GB/s/worker only with balanced candidate partitioning. | 1,000 / 2,000 / 4,000 offered QPS. Measure fan-out/merge and updates. Do not multiply global candidates by eight silently. |
| R2 • Multi-vector B; A correctness spike | Illustration: 1,000 candidate documents ×128 vectors ×128 FP16 dimensions =32.768 MB/query. At 500 QPS:16.384 GB/s useful before amplification. Query token count changes compute. | 100 / 250 / 500 QPS. Proposed P99 scorer ≤50 ms; judged relevance plus MaxSim correctness. Representation generation stays on reference GPU initially. |
| L1 • Local model A optional → B replicas | Qwen3-8B or Qwen3-30B-A3B reference. Pin precision, compiled pack, LPDDR/KV and operators. Capacity fit is only the first screen. | 4K input /128 output; 1 then 4 active sequences. Proposed P95 TTFT ≤2 s, TPOT ≤100 ms. Retain GPU path if unmet. |
| L2 • Cooperating MoE C; B extension only | Qwen3-235B-A22B first group; DeepSeek-V3 larger study. Measure per-rank weights/KV, expert routing and dispatch/combine. | 4K /8K inputs, 128 /256 outputs, 1 then 4 active sequences. Initial objective P95 TTFT ≤5 s, TPOT ≤100 ms; customer must approve. |

HOW THROUGHPUT BECOMES A RELEASE SPECIFICATION Publish the highest sustained accepted rate that meets the frozen quality, latency, error and recovery contract, with the tested hardware/software revision. Report offered, rejected and completed work separately. Four streams each sustained at 10 output tokens/s would require 40 aggregate tokens/s; that is demand arithmetic, not an ATMOS result.

R1 source arithmetic and 20 ms illustrative target: [I3, §§11,17 and Appendix A]. R2 and L1/L2 load/SLO choices are new test proposals. Benchmark models [R29–R32].

MODEL FIT • EXECUTION STILL NEEDS PROOF

# Representative models and resource screens

These models are reproducible study references—not known customer selections or a promised ATMOS model catalog. Use licensed, pinned checkpoints and actual converted pack sizes. BGE-M3/ColBERT feature generation may stay on GPUs while ATMOS executes only the scoring primitive.

| Reference / operation | Capacity or shape screen | Proposed placement |
| --- | --- | --- |
| BAAI/bge-m3 representations | 1,024-dimensional dense vectors in the public model. One FP16 vector is 2,048 bytes. 40M vectors =81.92 GB before metadata. | A: one local R1 shard. B: larger corpus and independent shards. No Day-1 embedding-generation claim. |
| ColBERTv2 / MaxSim study | Select the exact representation layout; R2 uses illustrative 128-dimensional token vectors. Variable document lengths affect reads and compute. | A correctness/reference; B optional R2 after gather/reduction and quality gates. |
| Qwen3-8B | Approximately 8B-class weights; raw bytes are only a rough screen. Compiled pack, scales and KV require measured accounting. | A optional local-model candidate; B independent replicas. |
| Qwen3-30B-A3B | 30.5B total /3.3B active. Raw 8-bit weights 30.5 GB; 16-bit 61 GB. Small-model KV can still constrain LPDDR. | A or B local model only with full operator and working-memory support. |
| Qwen3-235B-A22B | 235B total /22B active. Raw 8-bit 235 GB →≥3 ×100 GB allocations; 16-bit 470 GB →≥5. | C complete group; B group optional. Actual per-rank layouts may require more workers. |
| DeepSeek-V3 | 671B total /37B active. Raw 8-bit 671 GB →≥7 allocations; 16-bit 1,342 GB →≥14. | One C card is a raw 8-bit capacity screen only. 16-bit screen needs ≥2 eight-module cards, plus valid partitioning. |

## A no-fit result must remain visible

For an illustrative dense model reading 8 GB of uncached weights per decode step, a 100 ms step budget needs at least 80 GB/s useful weight delivery, before other work. A two-pass, combined-50 GB/s LPDDR path limited to 25 GB/s cannot satisfy that uncached single-stream case merely because HBF is labeled 200 GB/s. Cache, batching or quantization changes require an explicit new experiment.

Model/capacity basis [I1, pp.14–17], public model cards [R29–R32]. Raw byte screens exclude scales, shared tensors, alignment, code, workspace and safety budgets. The dense 8 GB example is a new analytical illustration.

HIGH-LEVEL DISCOVERY ONLY • NO CUSTOMER MODEL ATTRIBUTION

# Vertical use cases and phase demand

Ask each account to confirm its actual model, representation, service owner and buying authority. The names below are reference choices for discovery, not the models used by the named organizations in earlier case studies.

| Vertical / operator | Initial use case and reference | Demand / phase assignment |
| --- | --- | --- |
| Financial services | Policy/research evidence refinement using BGE-M3 dense representations; optional Qwen3-8B/30B-A3B for approved local drafting. | A: one authorized scoring stage. B: larger governed corpus. C: larger reasoning/MoE only when quality gain and deployment authority justify it. |
| Insurance | Claims/policy document matching; BGE-M3 or ColBERTv2-style multi-vector reference. | A: fixed-candidate scoring. B: richer representations, update/version consistency and tail latency. C is not required for the initial retrieval job. |
| Enterprise search / legal / engineering | Technical evidence search; dense BGE-M3 or bounded ColBERTv2/MaxSim. | A: local shard; B: capacity, fan-out, merge and richer features. Quality, deletions and freshness remain partner-owned. |
| Commerce / recommendation | Read-mostly item-feature lookup and scoring; use the customer’s pinned embedding table/model. No arbitrary substitute model is assumed. | A: trace discovery and primitive test. B: hot-item skew and pooled features. Defer write-heavy user state until endurance/update behavior is known. |
| Healthcare / life sciences | Authorized literature or operational-document retrieval; BGE-M3/ColBERT reference, not diagnosis. | A/B: bounded non-clinical retrieval evaluation; customer validation/data governance mandatory. No medical decision claim. |
| Private AI / service operator | Local model catalog and selected large MoE: Qwen3-8B, 30B-A3B, 235B-A22B; DeepSeek-V3 stretch study. | A/B: qualified replicas. C: complete cooperating group; strict KV/activation/collective budget. Model availability does not establish runtime support. |

## One workload card per opportunity

Record model/representation ID and hash; precision; prompt/output or candidate distributions; total and hot working set; quality/freshness target; peak/burst load; P95/P99 latency; failure requirement; current GPU/CPU/storage configuration; removable cost; and the named infrastructure owner. Route the card to A, B, C or not a fit.

KEEP THE CUSTOMER SECTION BOUNDED The first cycle selects one workload owner, one maintained integration and one OEM fixture. JPMorganChase and Allianz remain illustrative case-study organizations from the source—not claims of ATMOS POCs. Google-related anchor scope must be confirmed through the account sponsor.

Vertical framing and customer qualification [I1, pp.22–26; I3, §§3–7,15–16]. Model references [R29–R32]. All vertical-to-phase mappings on this page are proposed.

DIRECT ENGAGEMENT • HARDWARE AND COMMERCIAL PATH

# Who Sandisk should engage directly

Direct means a Sandisk owner runs the technical/commercial interface and receives a controlled deliverable. “Now” means architecture discovery, not an award or purchase. Supplier selection remains contingent on compatibility, quotes and support.

| Counterparty / first route | Phase A / immediate ask | Phase B / Phase C deliverable | Sandisk owner |
| --- | --- | --- | --- |
| Authorized anchor customer; Google only through confirmed sponsor | Workload charter, access permission, exact service boundary, buying window. | B: topology/scale acceptance. C: complete-model value and conditional pilot criteria. | Account + solution architect |
| Dell • primary OEM | R770 direct E3.S feasibility, device power and actual lane/reset map. | B1/B2 fabric BOM and support owner; C XE7740-class card/thermal feasibility. | OEM/platform lead |
| HPE • alternate OEM | Bounded DL380 Gen12 alternative review and comparison quote. | Qualify an alternate only when primary risk or customer standard warrants it. | OEM + procurement |
| Microchip • Switchtec FAE / applications | PM50052 configuration, tools/access, eight-x4 map and endpoint interoperability workshop. | B: qualified Gen5 fabric. C/Gen6: exact supported part, x4 map and board-design support. | PCIe architect + FW |
| Broadcom • PCIe switch applications | PEX89048 fan-out and peer-routing review; equivalent RFI to avoid lock-in. | B/C: firmware/EEPROM profile, error/reset map, SDK/support and quote. | PCIe architect + procurement |
| Selected board partner: Serial Cables first inquiry; LR-LINK / c-payne alternatives | Confirm orderability, non-NVMe endpoint support, cables and configured port exposure. | B1 engineering fixture, then production support scope; C reference/layout guidance as contracted. | Lab/platform lead |
| Sandisk device, HBF, packaging and manufacturing teams • internal direct | Approve HBF/LPDDR path, PCIe/DMA contract, power envelope and validation vehicles. | B: eight-endpoint behavior; C: card BOM, thermal design, yield/test and lifecycle release. | Hardware + memory leads |

## Do not duplicate OEM supply-chain ownership

Begin with the OEM’s approved board/firmware path. Promote an ODM, retimer or BIOS supplier to direct engagement only when a blocking requirement requires a three-party review. Sandisk should still receive status and evidence through its OEM owner.

Candidate platforms and switch facts [R1–R8,R13–R16]; account/ownership basis [I1, pp.31–32; I3, §§15–16]. No supplier relationship or customer commitment is inferred from this matrix.

DIRECT ENGAGEMENT • SOFTWARE AND OPERATING PATH

# Runtime, emulation and platform partners

| Counterparty / role | A deliverable | B / C expansion | Sandisk owner |
| --- | --- | --- | --- |
| Tenstorrent • existing engagement reported by program owner | Separate signed scopes for emulator, NPU/compiler, kernels and LLM integration; supported operator/model matrix. | B peer/group runtime and telemetry; C compiled grouped execution, model placement and recovery. | Partner + runtime lead |
| Red Hat • proposed enterprise platform discovery | RHEL/OpenShift driver/operator packaging, security and support feasibility on chosen customer platform. | B topology-aware allocation and node recovery; C complete-group scheduling and upgrade compatibility. | Platform/SRE lead |
| Canonical • proposed lab OS / alternate Kubernetes support | Pin Ubuntu LTS/kernel/container prerequisites that Tenstorrent and OEM actually support. | Maintain supported kernel/driver builds; qualify Canonical Kubernetes only if selected by customer. | OS/platform lead |
| Zilliz / Milvus • proposed first retrieval integration inquiry | Review Knowhere or another maintained scoring boundary; preserve IDs, filters and snapshot semantics. | B sharded scoring, updates and failure behavior. No C integration unless a workload needs it. | Search/runtime lead |
| Vespa or Qdrant • conditional alternate, not parallel full build | Vespa for multi-vector/data-local control; Qdrant for quantization/rescoring control. Select one only after the interface study. | Promote when the anchor’s engine or R2 requirement makes it the actual integration owner. | Search + account lead |
| NVIDIA enterprise support / OEM GPU support • lab control | Keep existing DGX/RTX baselines healthy, versioned and optimized; collect representative traces. | GPU↔ATMOS peer path only as a distinct supported integration, not inherited CUDA compatibility. | Lab/performance lead |
| Customer operations / security / procurement | Data-handling approval, installation constraints, failure target and conditional procurement criteria. | Service acceptance, support escalation, release cadence and production deployment authorization. | Account + security + product |

THE SOFTWARE PROVIDER IS NOT THE SWITCH PROVIDER Broadcom/Microchip route PCIe transactions; they do not implement ATMOS model execution. Tenstorrent’s public software does not establish an ATMOS backend. Sandisk must assign every gap between command/driver, memory management, compiled operators, serving engine and Kubernetes lifecycle.

Tenstorrent public boundaries [R17–R20]; OS/orchestration [R21–R24]; Milvus [R28]. Alternative search routes are retained from [I3, §7]. Current engagement status is program-owner-reported [U1], not independently verified.

INDIRECT ENGAGEMENT • NAMED ACCOUNTABLE ROUTE

# Hardware dependencies to track, not ignore

Indirect means Sandisk does not run routine supplier meetings, but a direct partner/internal owner must provide status, evidence and escalation. The named companies below are candidates or ecosystem examples; the actual BOM must identify the selected supplier and revision.

| Dependency / named candidates | Direct owner / evidence to collect | Phase exposure / promote to direct when |
| --- | --- | --- |
| ODM / board design: Wiwynn; Quanta/QCT as an alternative inquiry | Selected OEM. Record who designs/manufactures the backplane, switch board and C card; obtain responsibility and lifecycle map. | B2/C. Promote for custom layout, power or manufacturing work. No particular OEM–ODM relationship is assumed. |
| CPU/root complex: Intel or AMD, selected by OEM | OEM/platform lead. Exact CPU/BIOS, root-port topology, peer routing, address space and generation support. | A/B/C. Promote for reproducible root-complex blocker or missing roadmap requirement. |
| UEFI/BMC supply: AMI, Insyde; OpenBMC only where selected | OEM owns BIOS/BMC integration and identifies its actual supplier. Require reset/power/telemetry behavior and release plan. | A preflight; B fabric controls; C card service. Promote if OEM cannot resolve firmware changes. |
| Retimers / clocking: Broadcom or Microchip; other OEM-qualified supplier | OEM/board partner. Exact part/firmware, Gen5/Gen6 channel and clock mode, link-margin/error evidence. | B/C primarily. Promote for channel reach, clock or mixed-generation failure. |
| Cables / connectors / backplane: Serial Cables; OEM-qualified Amphenol or Molex path | Board/OEM owner. Pin assembly and length, pinout, sidebands, approved signal/power model and replacements. | A bay support; B MCIO; C internal channel. Promote for custom harness or sideband requirement. |
| LPDDR / controller IP / foundry / package / test suppliers | Sandisk procurement and silicon teams. Selected vendors/parts are not in the supplied sources; record controlled IDs, lead times and owner. | A–C critical. Promote for bandwidth, pinout, yield, endurance or supply risk before design freeze. |
| NIC/DPU: NVIDIA Networking or Broadcom, if selected | OEM/network lead. NIC/driver/firmware versions, PCIe demand, host placement and declared network service. | B replicated nodes; C multi-card/multi-node. Promote for GPU/NIC peer or collective bottlenecks. |

Ownership model [I1, pp.10,30–32]; firmware/ODM public references [R25–R27,R34]. Unselected supplier names are inquiry candidates, not established component content or compatibility claims.

INDIRECT ENGAGEMENT • SOFTWARE, STANDARDS AND LIFECYCLE

# Software dependencies and status discipline

| Dependency / named project | Accountable direct route | Required status / escalation trigger |
| --- | --- | --- |
| vLLM upstream; Tenstorrent plugin | Tenstorrent + Sandisk runtime owner | Pin compatible commits, models, interfaces and license/SBOM. Escalate upstream only for a reproducible framework blocker or accepted contribution. |
| Kubernetes upstream / CNCF ecosystem | Red Hat or Canonical + Sandisk platform owner | Track device-plugin/DRA API, security and supported distribution versions. Upstream is not a contracted product-support vendor. |
| Linux kernel PCI / IOMMU / P2PDMA | OS vendor + Sandisk driver owner | Track supported peer mapping, hot-remove/reset lifecycle, regression and CVEs. Upstream engagement when a reviewed fix is needed. |
| PyTorch / ONNX / model conversion dependencies | Tenstorrent compiler lead + Sandisk runtime | Exact exported graph and supported operator set. Do not infer arbitrary PyTorch execution from model import success. |
| Model publishers: Qwen/Alibaba, DeepSeek, BAAI, ColBERT maintainers | Sandisk model/runtime + legal owners | Checkpoint/license/quantizer hashes, permitted distribution, numerical test and security review. Direct contact only for rights or blocking implementation questions. |
| Search engine upstream: Milvus, Vespa, Qdrant, OpenSearch | Selected integration partner + Sandisk search owner | Extension compatibility, filtering/snapshot behavior and maintained release boundary. Add another engine only after a funded demand decision. |
| PCI-SIG / SNIA / DMTF standards | Sandisk PCIe/platform standards owners | Applicable PCIe/EDSFF/management revisions and compliance scope. A standards claim is not complete service qualification. |
| Registry, signing, SBOM, telemetry and CI dependencies | Sandisk security/release/SRE owners | Approved services and versions, offline install, update provenance and vulnerability remediation. Choose named tools through company policy, not this document. |

## Minimum record for every indirect item

Record dependency ID; selected supplier/project and version; Sandisk owner; direct partner carrying the interface; needed-by gate; last verified date; next evidence; open blocker; mitigation; escalation date. Review blockers weekly, stable items monthly, and every changed dependency at release freeze.

STATUS VOCABULARY Unconfirmed → requirements agreed → evidence received → lab validated → OEM/service qualified → released. “Supplier supports PCIe” is evidence received at most; “we had a meeting” is not compatibility.

Runtime and upstream sources [R17–R24,R28–R32]; release governance [I1, pp.28–30,39–40]. Status process and escalation policy are new recommendations.

VENDOR SELECTION • PROPOSED ENGINEERING PRIORITY

# Gen5 switch silicon: ordered shortlist

The first B map is 1 × x16 host + 8 × x4 ATMOS = 48 lanes and nine ports. All candidates must pass the actual port-grouping, endpoint, power and software gates. The ranking below is a provisional engineering preference—not a price or measured-performance ranking.

| Priority / exact choice | Published specification / fit | Reason and condition |
| --- | --- | --- |
| 1 • Microchip PM50052 | Switchtec PFX Gen5, 52 lanes /28 ports; published In Production. 48-lane target map leaves four lane positions in arithmetic. | Engineering-first inquiry: documented reference platform and ChipLink path. Require vendor-confirmed x16 +8×x4 map and compatible board firmware. |
| 2 • Broadcom PEX89048 | PEX89000 Gen5 family, 48 lanes. Exact lane budget for host x16 plus eight x4 workers. | Strong fixed-eight-worker alternative; base fan-out mode and accelerator endpoint use are documented. Promote to #1 if OEM-approved board/support and total cost are better. |
| 3 • Microchip PM50100 | Switchtec PFX Gen5, 100 lanes; published In Production. More room for wider/more endpoints. | Use when extra GPU/NIC links, expansion or topology require them—not to make the same eight x4 workers faster. |
| 4 • Broadcom PEX89072 / PEX89088 / PEX89104 / PEX89144 | Gen5 family options: 72 /88 /104 /144 lanes. Width/generation configuration is product-specific. | Consider for hybrid or expanded fabrics after a concrete port map. Larger lane count alone does not justify price, power or board area. |
| Not a separate ranked part “Broadcom PEX89000” | This is a family name that includes PEX89048 and larger variants. | Procurement must quote an exact part/revision; do not compare a family label as if it were another 48-lane device. |

## Compatibility is a pass/fail gate before scoring

Require transparent support for a non-NVMe accelerator endpoint; actual BAR/address window needs; DMA/MSI-X; independent speed configuration; accepted ACS/IOMMU policy; reset/error containment; hot-plug policy; tools and support. A chip that passes can still be on a storage-only board that does not.

After mandatory gates, use a proposed weighted selection: 35% functional/topology fit, 25% enablement/support, 20% complete configured cost, 15% lifecycle/supply, 5% needed expansion. Leave cost unscored until written quotations exist; do not manufacture numeric vendor scores.

Primary product data: [R1–R5]. Priorities and weights are new recommendations. Chip pricing, OEM volume costs and ATMOS compatibility have not been established.

A CHIP IS NOT A READY ATMOS FIXTURE

# Boards, availability and cost boundaries

| Board / vendor | Verified public configuration | ATMOS decision / procurement status |
| --- | --- | --- |
| Serial Cables / Microchip PCI5-AD-x16HI-MG5-52 | PM50052 Gen5 reference path; four x4 MCIO connections plus one x16 straddle connection. Microchip documents evaluation/support and ChipLink access. | First enablement inquiry, not a claimed eight-x4 turnkey card. Confirm breakout/reconfiguration and delivery; surfaced maker listing says “coming soon.” |
| LR-LINK / Linkreal LRSV9500-4I | Advertised Broadcom PEX89048 Gen5 x16 adapter with four MCIO 8i connectors and support for eight x4 NVMe devices. | Useful exact-fan-out board candidate. Storage advertisement does not qualify ATMOS BAR/DMA/reset/firmware behavior. Request non-NVMe support statement and quote. |
| c-payne PM50052 MCIO switch board | 52-lane board; default x16 upstream +2×x16 +x4 downstream; six MCIO 8i plus one MCIO 4i. Maker lists €1,050. | Alternative lab vehicle only after supported eight-x4 configuration/breakout review. Board listing is not eight-x4 ATMOS proof; stock/delivery need confirmation. |
| c-payne PM50100 MCIO switch board | 100-lane board; default x16 upstream +5×x16 +x4; twelve MCIO 8i plus one MCIO 4i. Maker lists €2,000. | Only when extra links are useful. More configurable lane capacity does not imply qualified firmware or a lower-cost production route. |

Vendor listing snapshots checked 27 September 2026 [R5–R9]. Euro amounts are advertised board prices, not chip prices, firm quotes, landed cost or volume OEM pricing. Taxes/shipping, cables, backplane, power and support must be quoted separately.

## What the RFQ must price

Quote the configured switch board, exact firmware profile, MCIO assemblies, E3.S backplane, power/thermal parts, debug tools/license terms, engineering support/NRE, fixtures, qualification, spares, warranty, lead time, end-of-life notice and production-volume pricing. Keep Gen5 and Gen6 BOMs separate.

RECOMMENDED BUYING RULE Do not design a custom B1 switch card before an existing board fails a documented requirement. Conversely, do not buy an NVMe adapter solely because its lane count matches. Obtain written generic-endpoint support and a reproducible test plan first. No purchase has been made by this study.

Integration and escalation responsibility: [I1, pp.10,31–32]. Public board status must be reconfirmed at purchase; contradictory or incomplete storefront stock signals are not evidence of delivery availability.

FUTURE-PHASE CAPABILITY • ENGAGE EARLY, RELEASE SELECTIVELY

# Gen6 and P2P qualification gates

| Choice | First engagement / fit | Required evidence before adoption |
| --- | --- | --- |
| Gen5 B baseline | PM50052 and PEX89048 inquiry now; eight Gen5 x4 endpoints, Gen5 x16 host. | Non-NVMe endpoint function; supported map; actual payload/latency/contended behavior; production support owner. |
| Microchip Gen6 low-lane family | Public 48/64-lane direction supports x2/x4/x8/x16. First Gen6 technical inquiry for eight x4 workers. | Exact orderable part/revision, reference board, supply date, power, mixed-speed map and OEM Gen6 host. Family announcement is insufficient. |
| Broadcom PEX90000 family / PEX90144 candidate | Parallel Gen6 roadmap/architecture inquiry, particularly for larger or integrated fabrics. | Exact downstream x4 grouping, mode/firmware and approved C port map. Do not assume every large Gen6 part supports the needed map. |
| Mixed Gen5 endpoints / Gen6 uplink | Candidate B optimization when host traffic is limiting and the OEM has a real Gen6 root path. | Measure usable payload in each direction and mixed-generation translation/queue effects; no automatic zero-oversubscription claim. |
| Native Gen6 C card | Source target has internal Gen6 links and a Gen5 host connection. | Native endpoint PHY, package/board channel, clocking, firmware, errors and thermals; do not validate by a Gen5 surrogate. |

## P2P has four owners

Sandisk endpoint/FW: peer-visible buffers/apertures, programmable DMA, ordering, completion and reset. Switch vendor: routing, port map, diagnostics and accepted security configuration. OEM/OS: BIOS, IOMMU, address windows and failure containment. Tenstorrent/Sandisk runtime: buffer ownership, dependencies, collectives and safe retry/cleanup.

For retrieval and independent replicas, P2P is optional. For fine-grained MoE it can be important, but it only avoids the host uplink when the producer and consumer are on a supported peer route below that uplink. A GPU outside the fabric does not become local because the switch supports P2P.

NON-NEGOTIABLE QUALIFICATION Prove peer payload with counters, not just successful enumeration. Test simultaneous transfers, reset during DMA and cross-tenant isolation. Never disable security controls simply to obtain a preferred benchmark. Peer routing does not supply coherent memory or same-device HA.

Gen6 publications [R10,R11,R36]; peer-DMA lifecycle [R12]; ATMOS qualification rules [I1, pp.6,32]. Exact Gen6 procurement readiness and ATMOS peer capability remain open.

OEM SELECTION • FIXTURES, NOT LOGO COMPARISONS

# Platform preferences and the lane map

| Preference / public platform | Proposed use | What the OEM must return |
| --- | --- | --- |
| 1 • Dell PowerEdge R770 | A and B E3.S investigation. Public configurations include E3.S populations; this is not ATMOS qualification. | Chosen 8/16-device population, exact backplane/riser, direct-versus-switched paths, supported compute power and firmware modifications. |
| 1 • Dell PowerEdge XE7740 | C mechanical/thermal investigation and RTX control. Public platform supports Gen5 accelerator slots and E3.S storage options. | C card fit, power, cooling, slot spacing, partial populations and service replacement. GPU support does not certify ATMOS. |
| 2 • HPE ProLiant Compute DL380 Gen12 | Alternate A/B feasibility and quotation path. Public E3.S-capable server family. | Equivalent supported population and operational contract; promote for customer standard or primary-platform blocker. |
| 3 • Lenovo ThinkSystem SR650 V4 | Contingency A/B path; public Gen5 platform with E3.S options. | Exact CTO configuration and non-NVMe endpoint permission; do not fund a third full qualification without demand. |
| Conditional • Wiwynn / Quanta-QCT route | Direct platform co-design when the anchor buys ODM infrastructure or B2/C requires it. | Named design/manufacturing ownership, engineering access, firmware lifecycle and support contract; no assumed OEM relationship. |

## The host lanes saved by B must have a destination

At eight Gen5 x4 devices, A uses 32 routed host lanes; B can use 16. Ask the OEM to identify the specific reclaimed root port and physical connector and price the use: an x16 GPU/NIC, additional storage or another switch domain. If the board cannot reroute those lanes, the economic benefit may be zero.

A switch does not add E3.S slots. Increasing beyond eight devices requires available compatible bays, board paths, power/cooling and a supported population. An external enclosure is a new qualification and support scope, not a free extension of B.

## Required workshop exit artifact

Return one configuration ID with BOM, lane/NUMA map, endpoint and uplink generations, switch/retimer/cable revisions, address-space/reset matrix, BIOS/BMC requirements, thermal budget, engineering quote and single first-response owner. Declare unsupported P2P and removal modes explicitly.

Public platform references [R13–R16,R34]; original fixture/qualification framework [I1, pp.31–32]. Vendor order is a proposed engagement priority, not a benchmark ranking.

FIRMWARE AND DEVICE SOFTWARE • ACCOUNTABILITY

# The compatibility work Sandisk must own

Target standard switch silicon with an ATMOS-qualified configuration. New switch silicon is not a presumed requirement. The real work is the endpoint ABI, switch profile, board management, OS integration and reproducible system recovery.

| Layer / accountable lead | Phase A | Phase B | Phase C |
| --- | --- | --- | --- |
| Sandisk endpoint / FW | PCIe identity, BARs, queues, MSI-X, DMA bounds, signed images, health, model/shard registration. | Peer apertures if enabled; concurrent endpoints; switch-related timeout and reset behavior. | Module/group identity; card reset and partial failure semantics; internal fabric behavior. |
| Sandisk driver / memory management | Host buffers, ownership, mapping/unmapping, completion, numerical-safe errors and version ABI. | Peer provider/client orchestration, IOMMU mapping, revocation and in-flight failure handling. | Group buffer layout, cross-card route contract and complete teardown/recovery. |
| Microchip / Broadcom applications | Review endpoint requirements early; configuration/reference access. | Port map, EEPROM/FW, ACS/DPC, counters, firmware update and interoperability issue triage. | Native Gen6/internal fabric constraints and production card review as contracted. |
| OEM BIOS/BMC; AMI/Insyde/OpenBMC indirectly as applicable | Enumeration, 64-bit address space as required, power sequencing, service telemetry and kernel support. | Switch discovery, downstream hot-plug policy, error/reset isolation and firmware matrix. | Card power/thermal control, replacement process and complete-node support bundle. |
| Tenstorrent + Sandisk runtime | Command/operator agreement, buffers and compiled primitive correctness. | Peer ordering, dispatch/combine, supported fallback and timeout policy. | Model grouping, collectives, load/reload and per-rank capabilities. |

## Produce an interface agreement, not only a driver backlog

The agreement must define the peer-accessible memory type, address translation, memory visibility/fences, reset survival, work-completion ambiguity, retry safety and failure ownership. Sandisk owns HBF/controller behavior unless a signed partner scope explicitly assigns it elsewhere.

FAILURE EXAMPLE TO RESOLVE BEFORE SILICON If a worker resets during a posted peer write, which party prevents reuse of the destination buffer, detects incomplete work and rebuilds the logical request? Switch packet routing cannot answer this application/firmware question.

Required software workstreams and operational contracts [I1, pp.28–30]; generic fan-out and peer support [R1,R4,R12]; firmware suppliers [R25–R27]. All ATMOS API details remain engineering requirements.

EXISTING PARTNER • DISTINCT DELIVERABLES

# Tenstorrent: runtime and emulator work packages

Engagement status: active work is reported by the program owner. Confirm a named technical lead and two separate accepted scopes: (1) functional/performance emulator interfaces and (2) compiler/kernel/runtime/model enablement. Neither scope should silently imply the other.

| Work package | A / first delivery | B / C extension | Acceptance artifact |
| --- | --- | --- | --- |
| TT-1 • Emulator contract | Supported command/operator inputs; memory-block coverage; headless execution; units and timing fidelity. | Multi-endpoint/topology hooks and C group behavior where supplied; Bridge retains system scheduling. | Versioned API, licensing/machine requirements, supported/unsupported blocks and golden traces. |
| TT-2 • Primitive/compiler path | Gather, dot/distance, masking, reduction/top-k; one local model only when operators and precision are supported. | MaxSim and selected MoE kernels; model lowering, per-rank layout and explicit fallback. | Compiled pack + numerical tolerances + operator matrix + reproducible build. |
| TT-3 • Serving backend | Agree the maintained engine integration; connect actual ATMOS execution, not a timing stub. | Multi-worker dispatch, KV/weight ownership, group collectives and performance counters. | Pinned engine/plugin/runtime/driver compatibility manifest and full-request tests. |
| TT-4 • Operations / support | Error taxonomy, initialization, health, drain and safe reset. | Peer failure, group restart, versioned upgrade and cross-card limitations. | Joint support runbook, issue-triage ownership and regression acceptance. |

## Public software is a reference, not the ATMOS contract

TT-Metal/TT-NN, tt-umd and tt-inference-server describe parts of Tenstorrent’s public stack. They do not establish support for ATMOS HBF, its controller, custom memory map or the proposed card. The older tenstorrent/vllm fork is marked deprecated; the public route now points to vllm-tt-plugin alongside upstream vLLM. Pin the partner-approved route and commits rather than freezing the obsolete fork.

PRESERVE THE BRIDGE’S ROLE Sandisk’s Bridge should remain the trace runner, resource/queue model, topology/placement study and evidence/reporting system. Consume partner timing or functional results through adapters. Available block-level RTL is not automatically a full HBF/controller/OEM model or a physical performance result.

Internal partner coverage and assumptions [I2, §§3,11,11.4–11.5]; public repositories and deprecation status checked 27 September 2026 [R17–R20]. February 2027 milestone must be reconfirmed.

KUBERNETES, LINUX AND THE CUSTOMER OPERATING MODEL

# A service needs more than a running pod

Recommended route: Sandisk owns the ATMOS device plugin/operator and recovery behavior; the chosen enterprise distribution vendor owns its supported platform contract. Begin with one supported Linux/container combination, then qualify the customer’s Kubernetes distribution.

| Decision / owner | A baseline | B expansion | C complete-group release |
| --- | --- | --- | --- |
| OS • Canonical or Red Hat, chosen with TT/OEM | Pin OS, kernel, compiler/runtime prerequisites and driver install/signing. | Regression across switch FW, DMA and peer mappings. | Card/native Gen6 support and grouped runtime combinations. |
| Allocation • Sandisk plugin/operator | Whole independently supported E3.S worker; capabilities and health discovery. | NUMA/switch-domain metadata; topology-aware placement and complete shard replicas. | Allocate valid complete model groups; do not advertise eight devices if hardware exposes only a card/group. |
| Orchestration • Red Hat primary enterprise inquiry; Canonical alternate | Install/upgrade, least privilege, admission, registry/offline deployment and monitoring. | Traffic drain, node/switch failure, model/shard reload and rollback. | Coordinated group rollout and recovery; multi-card scheduling only after explicit support. |
| API strategy • distro + Sandisk | Device plugin as initial integration where supported. | Evaluate DRA only against the chosen supported distro/API and resource needs. | Use topology/group capabilities without assuming DRA itself executes collectives or recovers models. |
| Customer operations | Service objective, allowed maintenance, incident routing and telemetry retention. | Degraded capacity and update windows under real load. | Complete-group RTO, work lost and fleet failover acceptance. |

## Define recovery at the application boundary

A device marked unhealthy does not automatically migrate the workload that already used it. A restarted pod does not restore a missing representation shard or model state. The operator/runtime must provide valid replicas, readiness checks, request retry semantics and enough surviving capacity for the agreed failure case.

Keep upstream Kubernetes, Linux and vLLM indirect initially, routed through the distro/vendor and the Sandisk owner. Promote a dependency to direct upstream work when a reproducible blocker requires a reviewed patch; maintain backport and release ownership.

Kubernetes device health and allocation [R21]; DRA [R22]; enterprise distribution references [R23–R24]; ATMOS operational requirements [I1, pp.28–30]. No Red Hat/Canonical ATMOS certification is established.

EXPERT PLACEMENT • TRAFFIC COMES FROM A PRODUCER

# MoE placement across A, B and C

The expert partition is not determined by the enclosure name. Place experts from actual activation producers, routing frequency, per-rank memory and execution load. Experts selected together do not necessarily communicate with one another; the important edges are dispatch and combine paths.

| Topology | Placement / execution implication | Test that decides value |
| --- | --- | --- |
| A • Direct-attached | Keep a host-coordinated baseline. Prefer complete local replicas where possible; for a studied split, minimize root/NUMA crossings and balance expert demand. | Host buffers/CPU overhead versus valid root-complex peer paths. Do not assume root traversal always copies through host DRAM. |
| B • Switch, no enabled P2P | The same expert partition may run, but host-facing traffic shares the uplink. A switch alone does not make expert parallelism more efficient. | Dispatch/combine under simultaneous workers, background loads and queueing; compare against equal-worker A. |
| B • Verified peer domain | Keep producer/consumer traffic local to the switch when the runtime and endpoints support it. Replicate hot experts only when useful and affordable. | Per-port peer bytes, hot destinations, scheduling delay and cross-domain traffic. A producer GPU above/outside the switch still uses its host path. |
| C • Integrated group | Use the on-card fabric for a validated complete model group; explicit ownership for attention/router/KV/shared tensors. | Per-rank weights/KV, internal synchronization, module skew and complete-card failure/recovery. |
| Multiple switch domains / cards | Partition from the measured traffic graph and load; preserve complete logical service under the declared failure policy. | Cross-domain bytes, full-group latency, replica reserve and reconfiguration time—not only capacity sum. |

## Communication budget to request from the customer/runtime

Per MoE layer, dispatch + combine ≈ 2 × T × d × b × k bytes

Here T is tokens in the routed batch, d hidden dimension, b bytes/value and k selected experts. This is a simple no-coalescing traffic screen, not a universal implementation count. Grouping experts on a worker, padding, metadata, tensor parallelism and producer placement change it. Measure link direction separately because PCIe is full duplex.

P2P QUALIFICATION IS NOT A COLLECTIVE IMPLEMENTATION The switch routes transactions. Tenstorrent/Sandisk must supply supported dispatch/combine or collective algorithms, completion ordering and failure semantics. Keep large-group enablement gated even when a simple peer copy succeeds.

Expert residency/traffic and strong controls [I1, pp.17,19,32]; peer routing/lifecycle [R12]. Traffic formula and placement policies are proposed analytical screens requiring actual traces.

CUSTOMER ENGAGEMENT • AN EXCHANGE OF EVIDENCE

# What customers receive before silicon

The offer is a time-boxed architecture and trace study: define the problem, establish an optimized baseline, identify the ATMOS requirements, and agree what future physical evidence would justify a pilot. Do not ask the customer to wait for hardware without receiving useful work.

| Engagement stage | Customer commitment | Sandisk deliverable / decision |
| --- | --- | --- |
| 1 • Qualify the owner | Service owner + infrastructure authority, current bottleneck and permitted initial profile. | One-page workload card, A/B/C route and initial no-fit screen. |
| 2 • Freeze the experiment | Authorized trace/model/representation; quality, freshness, latency and failure policy. | Measured DGX/RTX/CPU control, fixed data/precision and evaluation agreement. |
| 3 • Pre-silicon assessment | Engineering owner reviews assumptions and deployment constraints. | Bridge sensitivity, required HBF/compute/link envelope, topology options and unresolved capability list. |
| 4 • Reference integration | Maintained engine boundary and data/entitlement semantics. | CPU/GPU functional integration; versioning, failure and operational gap tests. Explicitly not ATMOS execution. |
| 5 • Conditional hardware pilot | Buying window, success/stop criteria and approved non-production deployment plan. | Versioned future test contract for A, B or C. Proceed, bounded redesign or no fit. |
| 6 • Physical acceptance | Actual approved deployment configuration and operational participation. | Measured service, recovery and economic result; support/release decision only after readiness gates. |

## Phase-specific customer message

A: prove one useful local stage and an installable device contract. B: justify a larger corpus, shared connectivity or a qualified peer fabric within the real OEM limits. C: justify a complete larger-model group whose quality and economics require the additional integration. A customer can stop at the simplest adequate offering.

## Commercial boundaries

Account, legal and procurement owners agree data/IP rights, permitted disclosure, publication approval, co-funding, support effort and hardware custody. Record interest, funded evaluation, design-in intent and purchase order separately. Do not use a partner logo or claim model adoption without authorization.

Partner exchange, workshop and commercial stages [I3, §§3,15,19–20 and Appendix C]. This document performs no outreach and invents no contacts or commitments.

USE THE EXISTING LAB • PRESERVE EVIDENCE CLASSES

# DGX/RTX, Bridge and partner validation

| Vehicle / accountable owner | What to do now | A / B / C evidence boundary |
| --- | --- | --- |
| DGX / RTX servers Lab + performance | Inventory exact GPU/CPU/NUMA/PCIe/storage/software. Run optimized resident references, retrieval primitives and model correctness. | Real control-platform measurements only; not ATMOS throughput or physical E3.S qualification. |
| ATMOS Bridge Solution architect + modeling | Model queues, HBF/LPDDR/NoC/DMA, real topology and scheduling; sweep unknowns and keep conservative profiles. | Requirements and sensitivity for A/B/C. A deterministic simulation is not semantic LLM execution or real p99. |
| Tenstorrent emulator / RTL Partner interface owner | Run documented commands/operators; compare golden microtraces and functional results within coverage. | Calibrate supported blocks; do not infer HBF, host or full-system behavior when not supplied. |
| Switch + surrogate endpoints PCIe/FW + OEM | Use capable FPGA/development endpoints to exercise BAR/DMA/peer/reset behavior on a qualified lab fixture. | Characterizes surrogate/switch/root path. It does not prove actual ATMOS DMA, native Gen6 or power. |
| Physical ATMOS engineering build Validation + hardware | Replay the same manifests on the exact endpoint/card, firmware and OEM path. | A local execution; B fabric effects; C complete-group behavior. Promote only observed, reproducible results. |
| Complete service / customer pilot Customer + release/SRE | Load, updates, security, installation, failure drills, support and quote-backed economics. | Production acceptance belongs to a complete named service configuration, not an isolated bandwidth microtest. |

## One experiment identity across all vehicles

Version device, topology, model, workload, policy and evidence profiles with a run ID. Collect useful bytes, physical bytes, queue/stall time, accepted rate, latency distributions, temperatures, errors and retries. Nsight Systems and DCGM can help instrument NVIDIA controls; pin tools and avoid conflicting profiling-counter sessions.

FIRST THREE EXPERIMENTS P0: local useful read delivery and staging/window limits. P1: fixed-candidate refinement against strong controls. L1: one bounded local model as a control. Add B host-versus-peer traffic and C grouped execution only when they answer a reviewed requirement.

Lab and evidence ladder [I1, pp.31–34; I2, §§3,5,7–9,11.5]; NVIDIA instrumentation [R35]. No hardware replacement, purchases or tests have been performed by this document.

EXECUTION SCHEDULE • RELATIVE GATES, NOT LAUNCH DATES

# First 90 days and the silicon bridge

| Window | Direct engagement / engineering output | Decision gate |
| --- | --- | --- |
| Days 1–15 | Ratify A/B/C names; confirm anchor and Tenstorrent scopes; appoint Sandisk owners. Send identical switch RFIs to Microchip/Broadcom; open Dell primary and HPE alternate feasibility. | Approved workload card, source-target ledger, access/NDA plan and phase backlog. |
| Days 16–30 | Lab baseline; actual lane/BAR/DMA/reset requirements; partner emulator interface; select one scorer integration. Identify supported OS/Kubernetes route. | One reproducible reference, one exact fixture candidate, and top five unresolved requirements. |
| Days 31–60 | P0/P1 models and controls; board configuration quote; surrogate path testing if available; TT primitive/backend spike. Start C design-freeze questions. | A feasible envelope or explicit no fit; B route/board decision; C hardware blockers assigned. |
| Days 61–90 | Independent evidence review; customer/OEM workshop; bounded software failure tests; versioned runtime/operator contract and RFQ comparison. | Evaluation package and conditional pilot plan. Continue, one time-boxed redesign, or stop the workload route. |
| Before partner/silicon milestones | Refresh model/runtime dependencies, validate partner coverage and complete joint regression harness. Recheck public parts and prices at procurement. | Replace assumptions with higher-fidelity evidence without relabeling simulations as measurements. |
| At usable silicon, currently assumed 2028 | Qualify A-D/A-P; B-D/B-P after fabric gates; C-D/C-P after native card/group gates. Work may overlap. | Signed service release only after function, performance, operations and support acceptance. |

## Milestones to obtain from Tenstorrent and hardware leadership

Separate emulator availability, compiler/kernel readiness, silicon design freeze, first silicon, engineering samples, card/backplane build and customer-ready release. Reconfirm the old February 2027 emulator assumption. The 2028 silicon assumption cannot supply any of those intermediate dates.

## Meeting cadence

Weekly: engineering blockers and indirect dependency freshness. Biweekly: A/B/C architecture decisions and supplier action review. Monthly: workload economics, customer progress and scope/resource decisions. At each release: frozen compatibility manifest and approved external claims.

Relative windows and governance [I1, pp.37–40; I2, §§10–13; I3, §19]. Calendar windows above are proposed execution planning, not signed supplier schedules.

SERVICE ACCEPTANCE • RESOURCES AND ACCOUNTABILITY

# Who signs each readiness gate

| Gate | Accountable Sandisk role | Required contributors / evidence |
| --- | --- | --- |
| G0 • Scope and specification | Product sponsor + solution architect | Customer service owner, hardware/NPU/memory leads. Approved interface, workload, source ledger and acceptance contract. |
| G1 • Function / safe device | FW/driver + validation leads | Tenstorrent and OEM. Correct primitives/model output, DMA bounds, versioning, reset and error handling. |
| G2 • Qualified service rate | Performance lead | Customer + runtime + OEM. Measured accepted throughput at quality/SLO; full traffic and update interference. |
| G3 • Operating / failure readiness | Platform/SRE lead | Customer operations, OS/Kubernetes partner and security. Install, upgrade, rollback, loss-of-device/switch/node/group and restore. |
| G4 • Economics / supply / support | Product + procurement + OEM lead | Written BOM/NRE/lifecycle quotes, complete-service cost, spare plan and single support escalation owner. |
| G5 • Release | Named release authority | All gate owners. Signed configuration/model manifest, limitations, reproduction package and permitted claims. |

## Staff functions, not a meeting-only partner network

Assign solution architecture/program ownership, performance modeling, search/runtime integration, firmware/driver, hardware/OEM, validation/security, release/SRE and account/procurement coordination. Partner liaisons need committed engineering time and an escalation path; a vendor logo is not a staffed deliverable.

The Master’s illustrative first-quarter envelope is 5.75 FTE /69 FTE-weeks for shared evidence and integration definition, not full silicon/compiler/production delivery. Reuse that as a scope discussion; do not add the Bridge and retrieval proposals’ overlapping budgets. With only the solution architect and periodic reviewers, limit the commitment to one workload, one model/path, one control and reviewed partner requirements.

AVAILABILITY MUST PRESERVE A COMPLETE SERVICE Place replicas across the declared failure boundary and size surviving capacity. Two four-worker switch domains containing different unique shards do not protect a query that needs all eight. Dual paths to the same device require explicit endpoint/firmware support and still do not protect against that device failing.

Resource envelope, ownership and gates [I1, pp.11,23,29–30,38–40]. Gate signatories and work allocation above are proposed; no staffing or budget is approved by this plan.

READY-TO-USE FIRST MEETINGS • NAMED COUNTERPARTIES

# Engagement packages and exit artifacts

| Meeting / participants | Send before the meeting | Require before closing the action |
| --- | --- | --- |
| Microchip Switchtec FAE Broadcom PCIe applications Sandisk PCIe/FW + procurement | Non-NVMe endpoint brief; x4 modes, BAR/DMA/MSI-X, clock/reset, power and peer requirements; 48-lane baseline and optional 64+ lane hybrid map. | Exact chip/board/configuration, no NVMe-only dependency statement, tools/NDA, owner, quote and joint interoperability plan. |
| Dell / HPE platform engineering Sandisk OEM + hardware | A/B/C diagrams, E3.S/2T envelope, direct/switched population, C card concept and failure/service targets. | Configuration ID, lane/bay/riser map, reset/power/thermal matrix, BIOS/BMC scope, qualification access, price and support owner. |
| Tenstorrent runtime/compiler/emulator Sandisk runtime + memory/FW | P0/P1 microtraces, candidate local model, HBF/LPDDR data path, command and peer semantics, evidence labels. | Separate scopes and milestones; supported blocks/operators; pinned integration route; golden tests and defect triage. |
| Red Hat / Canonical Sandisk platform/SRE + TT | Selected OS/kernel prerequisites, driver install model, container privileges, whole-worker/group contract and failure behavior. | Supported version plan, operator/driver responsibility, security constraints, certification route if required and support boundaries. |
| Selected customer + Zilliz/Milvus or actual engine owner Sandisk account + search | One-page workload card, measured baseline method, scorer request/snapshot/filter semantics and A/B/C scope. | Permitted trace, maintained adapter boundary, success/stop criteria, engineering owner and conditional pilot decision. |

## Common RFQ wording

“We seek a qualified non-NVMe ATMOS accelerator path, not an NVMe compatibility assertion. Identify standard components, required configuration changes, required firmware/software work, unsupported functions, engineering dependencies and the accountable support entity. Quote prototype and production scope separately.”

## Common engagement record

Capture counterparty team and named contact; Sandisk owner; direct/indirect classification; phase; NDA/SOW ID; required artifact; evidence class; commitment date; need-by gate; risk; cost/lead-time validity; next meeting; and closure approver. Populate real people from authorized account records—do not infer contacts from public pages.

RFI packages are new work instructions derived from [I1, pp.30–32; I2, §11; I3, §15 and Appendix C]. They have not been sent, accepted or costed.

LEADERSHIP DECISION • MAINTAINED READINESS SCORECARD

# Approve the next evidence, not a future promise

| Open decision | Recommended starting position | Evidence that can change it |
| --- | --- | --- |
| Phase names and priorities | A direct; B switched; C integrated. A is the simplest release path; future-phase hardware decisions start now. | Anchor requirements and approved hardware design; never rename silently in contracts or source archives. |
| Gen5 switch inquiry order | Microchip PM50052 engineering-first; Broadcom PEX89048 parallel alternative. | Supported board map, OEM approval, total configured quotes, support and supply. No known chip-price winner. |
| Gen6 and P2P | Preserve endpoint/fabric feasibility before design freeze; do not block A retrieval on optional peer or Gen6 work. | Trace shows material benefit; exact endpoint/switch/OEM/runtime capability passes safety and service tests. |
| OEM / operating platform | Dell primary; HPE alternate; Lenovo contingency. Canonical lab route and Red Hat enterprise inquiry, subject to actual customer/TT requirements. | Selected customer infrastructure, returned BOM/firmware map, supported versions and qualification economics. |
| First customer workload | One bounded P1 refinement stage; P0 under it and a small local-model control alongside. | Authorized trace, maintained integration, useful HBF delivery and removable customer cost. |
| Day-1 product claim | Evaluation kit before silicon; physical developer kit and qualified service only after their gates. | Traceable actual ATMOS results and signed release/support manifest. |

## Initial status register • verify with accountable owners

| Item / route | Known status at this review | Next artifact / owner |
| --- | --- | --- |
| Tenstorrent • direct | Engagement reported; signed scope and dates not supplied. | Emulator/runtime SOW and capability matrix • partner lead |
| Anchor customer • direct | Engagements reported; selected model/trace and acceptance contract unconfirmed. | Authorized workload card • account + architect |
| OEM / switch / OS partners • proposed direct | Candidates prioritized; ATMOS agreement and qualification status unconfirmed. | Owned RFI/RFQ and exact configurations • platform/procurement |
| Firmware / upstream stack • indirect | Public capabilities identified; selected BOM/version compatibility not yet established. | Controlled dependency evidence • OEM + Sandisk SW leads |

Review last evidence date, next artifact, need-by gate and blocker weekly. Use unknown / evidence received / lab passed / qualified / released—not unsupported percent-complete estimates.

MANAGEMENT PROPOSAL Fund the bounded A evidence and integration work; authorize parallel B switch/OEM and C hardware/runtime requirement reviews; assign accountable liaisons and quote owners. Return in 90 days with a reproducible customer evaluation, vendor/BOM recommendation, capability gaps and a conditional hardware validation plan. Release investment follows evidence, including a valid no-fit outcome.

Planning synthesis of [I1–I3,U1] with current primary research [R1–R36]. Unresolved items include actual silicon interfaces, vendor quotations, Gen6 orderable map, customer model choice and signed partner scopes.

SOURCE REGISTER • INTERNAL AUTHORITY AND GEN5 PARTS

# References • 1 of 4

Public pages were reviewed on 27 September 2026. Pin exact revisions at experiment and purchase freeze. Click the source labels below to open the primary publication. Public specs support only their stated scope; proposed rankings and ATMOS mappings are this plan’s recommendations.

[I1] ATMOS_Program_Master_Proposal_v3.docx

Supplied 48-page master, 26 September 2026. Architecture targets, original offering names, workload limits, OEM/software gates and governance. Remains authoritative only within its draft status.

[I2] ATMOS_Bridge_Emulator_Implementation_Proposal.docx

Supplied 22-page implementation proposal. Backend/evidence boundaries, Tenstorrent assumptions and memory-first POC requirements.

[I3] ATMOS_E3S_Executive_Product_and_Partner_Proposal.docx

Supplied 29-page retrieval/partner proposal. Customer boundaries, trace studies, calculations and commercial gates.

[U1] Current program-owner direction and planning context

Explicit new A/B/C mapping; customer engagements underway; Tenstorrent runtime/emulator engagement reported; 2028 silicon assumption. No signed agreements supplied.

[R1] Broadcom • PEX89000 Gen5 managed-switch product brief

Lane-family options, independent port configuration, generic endpoints and base fan-out operation; not ATMOS qualification.

Product brief  |  PEX89048

[R2] Microchip • PM50052

Public 52-lane/28-port Gen5 device page and production status. Exact requested map still needs confirmation.

Product page

[R3] Microchip • PM50100

Public 100-lane Gen5 product and production status; no public chip quote used.

Product page

[R4] Microchip • Switchtec PFX Gen5 family brief

Family lane variants, diagnostics and containment. Storage failover illustrations are not ATMOS HA support.

Family brief

[R5] Microchip • 52-lane Gen5 reference design

Reference validation platform, configuration/debug access and partner support route.

Reference design

[R6] Serial Cables • PM50052 host development board

Four x4 MCIO plus x16 straddle layout; availability must be confirmed. Public listing surfaced as coming soon.

Board listing

SOURCE REGISTER • BOARDS, BANDWIDTH AND OEMS

# References • 2 of 4

[R7] c-payne • 52-lane PM50052 MCIO board

Default port layout and advertised €1,050 board price; not a chip or qualified eight-ATMOS price.

Board listing

[R8] c-payne • 100-lane PM50100 MCIO board

Default layout and advertised €2,000 board price; scope excludes a complete ATMOS system.

Board listing

[R9] LR-LINK / Linkreal • LRSV9500-4I

PEX89048 Gen5 x16-to-eight-x4 storage-oriented adapter; non-NVMe support remains an RFI item.

Product page

[R10] Microchip • Gen6 Switchtec family announcement

5 November 2025 article; low-lane-count 48/64-lane direction and width choices. Exact procurement configuration unconfirmed.

Family article

[R11] PCI-SIG • PCI Express 6.0 specification overview

64 GT/s, PAM4, FLIT/FEC/CRC and backward compatibility. Raw bandwidth is not application payload.

Specification overview

[R12] Linux kernel • PCI peer-to-peer DMA support

Provider/client/orchestration, routing/ACS and lifetime constraints; switch support alone is insufficient.

Kernel documentation

[R13] Dell • PowerEdge R770

Published E3.S platform configurations; no ATMOS support or chosen lane map is established.

Platform reference

[R14] Dell • PowerEdge XE7740

Published accelerator-server/Gen5 slot and storage configuration; not an ATMOS-qualified card host.

Platform reference

[R15] HPE • ProLiant Compute DL380 Gen12

Public server family with E3.S options; exact modified platform and support require OEM approval.

Platform reference

[R16] Lenovo Press • ThinkSystem SR650 V4

Product guide updated 24 September 2026; Gen5 platform and E3.S options. Exact CTO population required.

Product guide

SOURCE REGISTER • RUNTIME AND OPERATING STACK

# References • 3 of 4

[R17] Tenstorrent • TT-Metal / TT-NN

Public low-level and operator software; hardware support does not automatically extend to ATMOS.

Repository

[R18] Tenstorrent • tt-umd

Public user-mode driver reference; not a released Sandisk ATMOS driver/ABI.

Repository

[R19] Tenstorrent • tt-inference-server

Public inference deployment and model/hardware integration references; pin supported releases and scope.

Repository

[R20] Tenstorrent • vLLM migration and plugin

Legacy fork explicitly deprecated; current public guidance points to standalone vllm-tt-plugin with upstream vLLM. ATMOS support unestablished.

Deprecation notice  |  Plugin

[R21] Kubernetes • Device plugins

Allocation/health semantics; an unhealthy device does not automatically migrate an existing application.

Documentation

[R22] Kubernetes • Dynamic Resource Allocation

Versioned resource-allocation mechanism; distro support and ATMOS implementation need separate review.

Documentation

[R23] Red Hat • OpenShift

Enterprise Kubernetes platform reference; proposed engagement, no ATMOS certification claimed.

Platform

[R24] Canonical • Kubernetes and Ubuntu kernel lifecycle

Operating-system/orchestration support investigation; actual Tenstorrent/OEM version compatibility controls the choice.

Kubernetes  |  Kernel lifecycle

[R25] AMI • Aptio V

UEFI supplier reference; does not identify the actual firmware supplier of any selected OEM platform.

Product

[R26] Insyde • Product portfolio

Firmware supplier candidate for OEM-mediated dependency tracking, not an asserted ATMOS relationship.

Portfolio

[R27] OpenBMC • Upstream project

Track only when the chosen platform actually uses it; not an inference about Dell/HPE firmware internals.

Repository

SOURCE REGISTER • INTEGRATION, MODELS AND FUTURE FABRIC

# References • 4 of 4

[R28] Milvus • Knowhere

Vector execution integration candidate; a standalone scorer does not prove a maintained production adapter.

Documentation

[R29] BAAI • BGE-M3 model card

Public 1,024-dimensional dense representation and multi-function retrieval model reference.

Model card

[R30] Qwen • Qwen3 model cards

Representative 8B, 30B-A3B and 235B-A22B checkpoints; pin licenses, converted packs and exact runtime support.

8B  |  30B-A3B  |  235B-A22B

[R31] DeepSeek • DeepSeek-V3 model card

671B total /37B active reference; raw weight capacity is not serving feasibility.

Model card

[R32] ColBERT maintainers • ColBERTv2.0

Multi-vector retrieval reference. The R2 document/token counts are this plan’s illustrative test choices.

Model card

[R33] Kioxia • EDSFF E3 form-factor overview

E3.S/2T physical and format context; not an ATMOS power, protocol or hot-removal guarantee.

Form factor

[R34] Wiwynn • Data-center platform supplier

Named ODM/platform inquiry candidate only; no OEM supply relationship or ATMOS engagement is inferred.

Company reference

[R35] NVIDIA • Nsight Systems and DCGM documentation

Instrumentation for existing GPU controls, including profiling considerations; not ATMOS counters or calibration.

Nsight Systems  |  DCGM

[R36] Broadcom Gen6 / Synopsys interoperability reference

PEX90144 family candidate and 2025 PEX90000 interoperability demonstration. Neither establishes an eight-x4 ATMOS board or production availability.

PEX90144  |  Interoperability

CONTROLLED UPDATE RULE When a target, supplier, model, price, runtime or topology changes, update its dependent phase envelope, experiment, support matrix and approved claim together. Preserve old versions; do not silently reinterpret a prior result under the new A/B/C naming.